REQUEST FOR PROPOSAL (RFP)

INTEGRATED STRATEGIC DEVELOPMENT PLAN

FOR

LAHORE REGION 2035

June 2013

Lahore Development Authority (LDA)

Disclaimer

1. The information contained in this Request for Proposal (RFP) document or subsequently provided to Bidder(s), whether verbally or in written form by or on behalf of the Lahore Development Authority (LDA) or any of their employees or advisors, shall be subject to the terms and conditions set out in this RFP document and any other terms and conditions subject to which such information is provided.

2. This RFP document does not purport to contain all the information each Bidder may require. This RFP document may not be appropriate for all persons, and it is not possible for the LDA, their employees or advisors to consider the investment objectives, financial situation and particular needs of each Bidder who reads or uses this RFP document. Certain Bidders may have better knowledge of the proposed Project than others. Each Bidder should conduct its own investigations and analysis and should check the accuracy, reliability and completeness of the information in this RFP document and obtain independent advice from appropriate sources. LDA, its Representatives, their employees and advisors make no representation or warranty and shall incur no liability under any law, statute, rules or regulations as to the accuracy, reliability or completeness of the RFP document.

3. LDA may, in their absolute discretion, but without being under any obligation to do so, update, amend, add to any or all of the provisions or supplement the information of this RFP document or cancel the present Invitation and call for fresh Invitations. Such changes would be intimated to all Bidders using this RFP Document.

4. LDA reserves the right to reject any or all of proposals received in response to this RFP Invitation at any stage without assigning any reasons whatsoever. LDA also reserves the right to hold or withdraw from or cancel the process at any stage up to the final pre-qualification / short listing.

5. Neither LDA nor their employees or representative will have any liability in case of non receipt of any correspondence from them to the bidders due to the postal delays.

REQUEST FOR Proposal DOCUMENT

- Schedule of Qualification Process

This RFP is issued to the Bidder in response to the short listing of their Expression of Interests.

| Date & Time for pre-proposal conference | Tuesday, July 16, 2013 at 11:00am (Tentative date & time) CMP Wing, Lahore Development Authority, Committee Room, 467-DII Johar Town Lahore, Pakistan |
| --- | --- |
| Last date for receipt of queries | Wednesday, July 24, 2013, 5:00 pm Contact Person: Mr. WASEEM AHMAD KHAN, Chief Metropolitan Planner Ph: +92-42-99262332 Fax: +92-42-99262373 Email: cmpwinglda@gmail.com and info.isdp35@gmail.com |
| Last date for submission of Proposals in response to this RFP | Wednesday, July 31, 2013 at 3:00 pm at the CMP Counter, One Window Cell, Lahore Development Authority 467-DII Johar Town Lahore, Pakistan |
| Date and time of Opening of Technical Proposals in response to this RFP | Thursday, August 01, 2013 at 11:00 am (Tentative time) at the Committee Room, 467-DII Johar Town Lahore, Pakistan |

NOTICE INVITING REQUEST FOR proposal

Lahore Development Authority

INTEGRATED STRATEGIC DEVELOPMENT PLAN

for

LAHORE REGION 2035 (ISDP-35)

Urbanization, one of the key challenges of the new millennium, is taking place at a rapid rate and is unstoppable. The scale and complexity of urban problems are intensifying everywhere. Therefore, the urbanizing cities need to revisit and revitalise their strategic planning processes to address their future economic, social and environmental needs. Since a robust relationship exists between urbanization and per capita income, the cities have to urbanize to upgrade to the status from developing to developed cities.

The cities in Punjab are not only confronted with the task of managing unprecedented population growth, but are also under tremendous pressure to adequately cope with the resultant demands on urban land and infrastructure services.

The Government of the Punjab intends to develop urban areas of the Province as sustainable, livable and well managed engines of economic growth. The City of Lahore and its surrounding towns have expanded greatly accommodating almost half population of the Province, and hence require a comprehensive, strategic, regional, and long-term plan.

Therefore Lahore Development Authority (LDA) has been assigned the task to prepare the “Integrated Strategic Development Plan for Lahore Region – 2035 (ISDP-35)”. Since the scope of this Plan will be regional, Lahore Development Authority shall be the Client on behalf of all Districts of Lahore Division including Lahore, Sheikhupura, Kasur and Nankana Sahib.

The “Integrated Strategic Development Plan for Lahore Region 2035 (ISDP-35)” need to have regional focus and short to long term action and financing plans. In this regard, you firm has been shortlisted and invited to submit proposal as per this RFP.

Lahore Development Authority (LDA)

Contact: Mr. WASEEM Khan, Chief Metropolitan Planner

Ph: +92-42-99262332 Fax: +92-42-99262373

Email: cmpwinglda@gmail.com, website: www.lda.gop.pk

# TABLE OF CONTENT

SCHEDULE OF QUALIFICATION PROCESS...........................................................iii

ACRONYMS & ABBREVIATIONS..................................................................................vi

SECTION 1: LETTER OF INVITATION...........................................................................4

SECTION 2: INSTRUCTIONS TO BIDDERS.................................................................14

INSTRUCTIONS TO BIDDERS…………………………………………………………27

DATA SHEET…………………………………………………………………………….27

SECTION 3: TECHNICAL PROPOSAL - STANDARD FORMS................................31

FORM  TECH-1  TECHNICAL PROPOSAL SUBMISSION FORM………………...32

FORM  TECH-2  CONSULTANT’S ORGANIZATION AND EXPERIENCE……..33

Form  TECH-3  Comments and Suggestions on the Terms of Reference and on Counterpart Staff and Facilities to be Provided by the Client	35

FORM  TECH-4	DESCRIPTION OF APPROACH, METHODOLOGY AND WORK

PLAN FOR PERFORMING THE ASSIGNMENT	36

FORM  TECH-5  TEAM COMPOSITION AND TASK ASSIGNMENTS	37

FORM  TECH-6	CURRICULUM VITAE (CV) FOR PROPOSED PROFESSIONAL

STAFF	38

FORM  TECH-7  STAFFING SCHEDULE1	41

FORM  TECH-8  WORK SCHEDULE	43

SECTION 4:  FINANCIAL PROPOSAL - STANDARD FORMS................................44

FORM  FIN-1  FINANCIAL PROPOSAL SUBMISSION FORM	45

FORM  FIN-2  SUMMARY OF COSTS	46

FORM  FIN-3  BREAKDOWN OF COSTS BY ACTIVITY1	47

FORM  FIN-4  BREAKDOWN OF REMUNERATION1	48

FORM  FIN-5  BREAKDOWN OF REIMBURSABLE EXPENSES	49

SECTION 5: TERMS OF REFERENCE	50

REPORTING REQUIREMENTS:	63

APPENDIX 1A: FORMAT FOR POWER OF ATTORNEY FOR SIGNING PROPOSAL	64

APPENDIX 1B: FORMAT FOR POWER OF ATTORNEY FOR LEAD MEMBER OF CONSORTIUM	66

APPENDIX 2:DETAILS OF BIDDER	68

APPENDIX 3: FORMAT FOR LETTER OF PROPOSAL APPLICATION	69

APPENDIX 4: LETTER OF INTENT TO FORM A CONSORTIUM	70

APPENDIX 5: FORMAT FOR ANTI-COLLUSION CERTIFICATE	71

APPENDIX 6A: FORMAT FOR PROJECT UNDERTAKING	72

APPENDIX 6B: FORMAT FOR PROJECT UNDERTAKING	73

APPENDIX 7: FORMAT FOR MEMORANDUM OF UNDERSTANDING (MOU)	74

CHECKLIST OF DOCUMENTS TO BE SUBMITTED	75

STANDARD FORM OF AGREEMENT	75

# ACRONYMS & ABBREVIATIONS

| GoPb | Government of the Punjab |
| --- | --- |
| CDGL | City District Government, Lahore |
| DCO | District Coordination Officer |
| LDA | Lahore Development Authority |
| CMP | Chief Metropolitan Planner |
| ISDP-35 | Integrated Strategic Development Plan for Lahore Region 2035 |
| EOI | Expressions of interest |
| MOU | Memorandum of Understanding |
| RFP | Request for Proposal |
| POA | Power of Attorney |
| CF | Cash Flow |
| QCBS | Quality and Cost Based Selection |
| DG | Director General |

# SECTION 1: LETTER OF INVITATION

LAHORE DEVELOPMENT AUTHORITY

METROPOLITAN PLANNING WING

No: DMP/LDA /

DATED:

Mr. Parvez Latif Qureshi

Chief Executive

UNICON Consulting Services (Pvt)

82-Allauddin Road, Lahore Cantt.

SUBJECT: 	LETTER OF INVITATION

Dear Mr. Parvez Latif Qureshi,

- The LDA invites proposals to provide the following consulting services: for “Integrated Strategic Development Plan for Lahore Region 2035 (ISDP-35)”. Details on the services are provided in the Terms of Reference.

- The Consultant will be selected under the Quality and Cost Based Selection (QCBS) Method and procedures described in this RFP, in accordance with the policies of the Government of Punjab detailed in the Consultant Selection Guidelines issued by the Planning & Development Department.

- LDA now invites proposals to provide the consulting services as described in the Term of References in the Section 5.

- The request for Proposal has been addressed to the following shortlisted bidders:

Bidder 1: 	UNICON & AECOM

Bidder 2: 	MM Pakistan (Pvt.) Ltd., Mott MacDonald Limited UK, BELDA Planning and Consulting Ltd, Turkey and AJC Planning Company SDN BHD, Malaysia

Bidder 3: 	National Engineering Services Pakistan (Pvt.) Ltd.

Bidder 4: 	Osmani & Company (Pvt.) Ltd., Doxiadis Associates, Associated Consulting Engineers

Bidder 5: 	Engineering Consultants International (Pvt.) Limited (ECIL), Exponent Engineers (Pvt.) Ltd. and Varow International (Pakistan)

This invitation is not permissible to be transferred to any other firm/consortium.

- The RFP includes the following additional documents:

Section 2 - Instructions to Bidders (including Data Sheet)

Section 3 - Technical Proposal - Standard Forms

Section 4 - Financial Proposal - Standard Forms

Section 5 - Terms of Reference

- It is mandatory for proposals to be made using the Standard Forms of the RFP. Proposals that are not in the prescribed format may be discarded. If any information required in the forms is found missing or written elsewhere, no credit may be given in the relevant section of the evaluation.

- Bidders should submit their five most relevant assignments for technical evaluation using the prescribed format. Assignments submitted beyond the given number will not be considered.

- CVs of key personnel to be working on this assignment should be provided according to the list given in the Data Sheet.

- Technical and financial proposals should be submitted in Separate Sealed envelopes.

- This information should be sent to the following address:

Name: 		WASIM AHMAD KHAN

Designation: 	Chief Metropolitan Planner

Address: 		Lahore Development Authority, 467-DII Johar Town, Lahore

Email: 		cmpwinglda@gmail.com and info.isdp35@gmail.com

Ph: 		+92-42-99262332 	Fax: +92-42-99262341

If no acknowledgment is received, it will be presumed that the bidders are not interested in undertaking the assignment.

Yours sincerely,

KHALID HASSAN LODHI

Director Metropolitan Planning

CMP Wing, Lahore Development Authority

LAHORE DEVELOPMENT AUTHORITY

METROPOLITAN PLANNING WING

No: DMP/LDA /

DATED:

Mr. Qasim Bashir

Manager (Business Development)

2nd Floor, CTI Building,

27-Empress Road, Lahore

SUBJECT: 	LETTER OF INVITATION

Dear Mr. Qasim Bashir,

- The LDA invites proposals to provide the following consulting services: for “Integrated Strategic Development Plan for Lahore Region 2035 (ISDP-35)”. Details on the services are provided in the Terms of Reference.

- The Consultant will be selected under the Quality and Cost Based Selection (QCBS) Method and procedures described in this RFP, in accordance with the policies of the Government of Punjab detailed in the Consultant Selection Guidelines issued by the Planning & Development Department.

- LDA now invites proposals to provide the consulting services as described in the Term of References in the Section 5.

- The request for Proposal has been addressed to the following shortlisted bidders:

Bidder 1: 	UNICON & AECOM

Bidder 2: 	MM Pakistan (Pvt.) Ltd., Mott MacDonald Limited UK, BELDA Planning and Consulting Ltd, Turkey and AJC Planning Company SDN BHD, Malaysia

Bidder 3: 	National Engineering Services Pakistan (Pvt.) Ltd.

Bidder 4: 	Osmani & Company (Pvt.) Ltd., Doxiadis Associates, Associated Consulting Engineers

Bidder 5: 	Engineering Consultants International (Pvt.) Limited (ECIL), Exponent Engineers (Pvt.) Ltd. and Varow International (Pakistan)

This invitation is not permissible to be transferred to any other firm/consortium.

- The RFP includes the following additional documents:

Section 2 - Instructions to Bidders (including Data Sheet)

Section 3 - Technical Proposal - Standard Forms

Section 4 - Financial Proposal - Standard Forms

Section 5 - Terms of Reference

- It is mandatory for proposals to be made using the Standard Forms of the RFP. Proposals that are not in the prescribed format may be discarded. If any information required in the forms is found missing or written elsewhere, no credit may be given in the relevant section of the evaluation.

- Bidders should submit their five most relevant assignments for technical evaluation using the prescribed format. Assignments submitted beyond the given number will not be considered.

- CVs of key personnel to be working on this assignment should be provided according to the list given in the Data Sheet.

- Technical and financial proposals should be submitted in Separate Sealed envelopes.

- This information should be sent to the following address:

Name: 		WASIM AHMAD KHAN

Designation: 	Chief Metropolitan Planner

Address: 		Lahore Development Authority, 467-DII Johar Town, Lahore

Email: 		cmpwinglda@gmail.com and info.isdp35@gmail.com

Ph: 		+92-42-99262332 	Fax: +92-42-99262341

If no acknowledgment is received, it will be presumed that the bidders are not interested in undertaking the assignment.

Yours sincerely,

KHALID HASSAN LODHI

Director Metropolitan Planning

CMP Wing, Lahore Development Authority

LAHORE DEVELOPMENT AUTHORITY

METROPOLITAN PLANNING WING

No: DMP/LDA /

DATED:

Ms. Azra Zaigham

Vice President, A&P Division

National Engineering Services Pakistan (Pvt.) Limited

1-C Block-N, Model Town Extension, Lahore

SUBJECT: 	LETTER OF INVITATION

Dear Ms. Azra Zaigham,

- The LDA invites proposals to provide the following consulting services: for “Integrated Strategic Development Plan for Lahore Region 2035 (ISDP-35)”. Details on the services are provided in the Terms of Reference.

- The Consultant will be selected under the Quality and Cost Based Selection (QCBS) Method and procedures described in this RFP, in accordance with the policies of the Government of Punjab detailed in the Consultant Selection Guidelines issued by the Planning & Development Department.

- LDA now invites proposals to provide the consulting services as described in the Term of References in the Section 5.

- The request for Proposal has been addressed to the following shortlisted bidders:

Bidder 1: 	UNICON & AECOM

Bidder 2: 	MM Pakistan (Pvt.) Ltd., Mott MacDonald Limited UK, BELDA Planning and Consulting Ltd, Turkey and AJC Planning Company SDN BHD, Malaysia

Bidder 3: 	National Engineering Services Pakistan (Pvt.) Ltd.

Bidder 4: 	Osmani & Company (Pvt.) Ltd., Doxiadis Associates, Associated Consulting Engineers

Bidder 5: 	Engineering Consultants International (Pvt.) Limited (ECIL), Exponent Engineers (Pvt.) Ltd. and Varow International (Pakistan)

This invitation is not permissible to be transferred to any other firm/consortium.

- The RFP includes the following additional documents:

Section 2 - Instructions to Bidders (including Data Sheet)

Section 3 - Technical Proposal - Standard Forms

Section 4 - Financial Proposal - Standard Forms

Section 5 - Terms of Reference

- It is mandatory for proposals to be made using the Standard Forms of the RFP. Proposals that are not in the prescribed format may be discarded. If any information required in the forms is found missing or written elsewhere, no credit may be given in the relevant section of the evaluation.

- Bidders should submit their five most relevant assignments for technical evaluation using the prescribed format. Assignments submitted beyond the given number will not be considered.

- CVs of key personnel to be working on this assignment should be provided according to the list given in the Data Sheet.

- Technical and financial proposals should be submitted in Separate Sealed envelopes.

- This information should be sent to the following address:

Name: 		WASIM AHMAD KHAN

Designation: 	Chief Metropolitan Planner

Address: 		Lahore Development Authority, 467-DII Johar Town, Lahore

Email: 		cmpwinglda@gmail.com and info.isdp35@gmail.com

Ph: 		+92-42-99262332 	Fax: +92-42-99262341

If no acknowledgment is received, it will be presumed that the bidders are not interested in undertaking the assignment.

Yours sincerely,

KHALID HASSAN LODHI

Director Metropolitan Planning

CMP Wing, Lahore Development Authority

LAHORE DEVELOPMENT AUTHORITY

METROPOLITAN PLANNING WING

No: DMP/LDA /

DATED:

Mr. Dhani Bukhsh Magsi

Manager Business Development

Osmani & Company (Pvt.)  Ltd.

245/2-K, Block 6, PECHS, Karachi-75400, Pakistan

SUBJECT: 	LETTER OF INVITATION

Dear Mr. Dhani Bukhsh Magsi,

- The LDA invites proposals to provide the following consulting services: for “Integrated Strategic Development Plan for Lahore Region 2035 (ISDP-35)”. Details on the services are provided in the Terms of Reference.

- The Consultant will be selected under the Quality and Cost Based Selection (QCBS) Method and procedures described in this RFP, in accordance with the policies of the Government of Punjab detailed in the Consultant Selection Guidelines issued by the Planning & Development Department.

- LDA now invites proposals to provide the consulting services as described in the Term of References in the Section 5.

- The request for Proposal has been addressed to the following shortlisted bidders:

Bidder 1: 	UNICON & AECOM

Bidder 2: 	MM Pakistan (Pvt.) Ltd., Mott MacDonald Limited UK, BELDA Planning and Consulting Ltd, Turkey and AJC Planning Company SDN BHD, Malaysia

Bidder 3: 	National Engineering Services Pakistan (Pvt.) Ltd.

Bidder 4: 	Osmani & Company (Pvt.) Ltd., Doxiadis Associates, Associated Consulting Engineers

Bidder 5: 	Engineering Consultants International (Pvt.) Limited (ECIL), Exponent Engineers (Pvt.) Ltd. and Varow International (Pakistan)

This invitation is not permissible to be transferred to any other firm/consortium.

- The RFP includes the following additional documents:

Section 2 - Instructions to Bidders (including Data Sheet)

Section 3 - Technical Proposal - Standard Forms

Section 4 - Financial Proposal - Standard Forms

Section 5 - Terms of Reference

- It is mandatory for proposals to be made using the Standard Forms of the RFP. Proposals that are not in the prescribed format may be discarded. If any information required in the forms is found missing or written elsewhere, no credit may be given in the relevant section of the evaluation.

- Bidders should submit their five most relevant assignments for technical evaluation using the prescribed format. Assignments submitted beyond the given number will not be considered.

- CVs of key personnel to be working on this assignment should be provided according to the list given in the Data Sheet.

- Technical and financial proposals should be submitted in Separate Sealed envelopes.

- This information should be sent to the following address:

Name: 		WASIM AHMAD KHAN

Designation: 	Chief Metropolitan Planner

Address: 		Lahore Development Authority, 467-DII Johar Town, Lahore

Email: 		cmpwinglda@gmail.com and info.isdp35@gmail.com

Ph: 		+92-42-99262332 	Fax: +92-42-99262341

If no acknowledgment is received, it will be presumed that the bidders are not interested in undertaking the assignment.

Yours sincerely,

KHALID HASSAN LODHI

Director Metropolitan Planning

CMP Wing, Lahore Development Authority

LAHORE DEVELOPMENT AUTHORITY

METROPOLITAN PLANNING WING

No: DMP/LDA /

DATED:

Mr. Irfan Jan

Manager (D&C)

29 Block 7/8, D.C.H.S Darul-Aman, Co-operative Housing Society

Shahrae Faisal, Karachi

SUBJECT: 	LETTER OF INVITATION

Dear Mr. Irfan Jan,

- The LDA invites proposals to provide the following consulting services: for “Integrated Strategic Development Plan for Lahore Region 2035 (ISDP-35)”. Details on the services are provided in the Terms of Reference.

- The Consultant will be selected under the Quality and Cost Based Selection (QCBS) Method and procedures described in this RFP, in accordance with the policies of the Government of Punjab detailed in the Consultant Selection Guidelines issued by the Planning & Development Department.

- LDA now invites proposals to provide the consulting services as described in the Term of References in the Section 5.

- The request for Proposal has been addressed to the following shortlisted bidders:

Bidder 1: 	UNICON & AECOM

Bidder 2: 	MM Pakistan (Pvt.) Ltd., Mott MacDonald Limited UK, BELDA Planning and Consulting Ltd, Turkey and AJC Planning Company SDN BHD, Malaysia

Bidder 3: 	National Engineering Services Pakistan (Pvt.) Ltd.

Bidder 4: 	Osmani & Company (Pvt.) Ltd., Doxiadis Associates, Associated Consulting Engineers

Bidder 5: 	Engineering Consultants International (Pvt.) Limited (ECIL), Exponent Engineers (Pvt.) Ltd. and Varow International (Pakistan)

This invitation is not permissible to be transferred to any other firm/consortium.

- The RFP includes the following additional documents:

Section 2 - Instructions to Bidders (including Data Sheet)

Section 3 - Technical Proposal - Standard Forms

Section 4 - Financial Proposal - Standard Forms

Section 5 - Terms of Reference

- It is mandatory for proposals to be made using the Standard Forms of the RFP. Proposals that are not in the prescribed format may be discarded. If any information required in the forms is found missing or written elsewhere, no credit may be given in the relevant section of the evaluation.

- Bidders should submit their five most relevant assignments for technical evaluation using the prescribed format. Assignments submitted beyond the given number will not be considered.

- CVs of key personnel to be working on this assignment should be provided according to the list given in the Data Sheet.

- Technical and financial proposals should be submitted in Separate Sealed envelopes.

- This information should be sent to the following address:

Name: 		WASIM AHMAD KHAN

Designation: 	Chief Metropolitan Planner

Address: 		Lahore Development Authority, 467-DII Johar Town, Lahore

Email: 		cmpwinglda@gmail.com and info.isdp35@gmail.com

Ph: 		+92-42-99262332 	Fax: +92-42-99262341

If no acknowledgment is received, it will be presumed that the bidders are not interested in undertaking the assignment.

Yours sincerely,

KHALID HASSAN LODHI

Director Metropolitan Planning

CMP Wing, Lahore Development Authority

# SECTION 2: INSTRUCTIONS TO BIDDERS

| Definitions | - “Agreement” means the Agreement signed by the Parties and all the attached documents. - “Client” means the organization with which the selected Bidders sign the Agreement for the Services (Director General –Lahore Development Authority (DG-LDA) will be the Client) on behalf of all Districts within Lahore Division. - “Bidder” means any entity or consortium that may provide or provides the Services to the Client under the Agreement. - “Data Sheet” means such part of the Instructions to Bidders used to reflect specific conditions. - “Day” means calendar day. - “Government” means the Government of the Punjab and all its associated departments, agencies, autonomous/semi-autonomous bodies, local governments, boards, universities and similar other organizations. - “Instructions to Bidders” means the document which provides shortlisted Bidders with all information needed to prepare their Proposals. - “LOI” means the Letter of Invitation included in the RFP as Section 1 being sent by the Client to the Bidders. - “Personnel” means professionals and support staff provided by the Bidders or by any Sub-Consultant and assigned to perform the Services or any part thereof; “Foreign Personnel” means such professionals and support staff who at the time of being so provided had their domicile outside Pakistan; “Local Personnel” means such professionals and support staff who at the time of being so provided had their domicile inside Pakistan. - “Proposal” means the Technical Proposal and the Financial Proposal. - “RFP” means the Request for Proposal to be prepared by the Client for the selection of Bidders, based on the Standard RFP. - “Services” means the work to be performed by the Bidders pursuant to the Agreement. - “Sub- Bidders” means any person or entity with whom the Bidders sub-agreements any part of the Services. - “Terms of Reference” (TOR) means the document included in the RFP as Section 5 which explains the objectives, scope of work, activities, tasks to be performed, respective responsibilities of the Client and the Bidders, and expected results and deliverables of the assignment. |
| --- | --- |
| - Introduction | - The Client named in the Data Sheet will select a consulting firm/organization (the Bidders) from those to whom the Letter of Invitation issued, in accordance with the method of selection specified in the Data Sheet. - The shortlisted Bidders are invited to submit a Technical Proposal and a Financial Proposal for consulting services required for the assignment named in the Data Sheet. The proposals should be in separate marked and sealed envelopes. The Proposal will be the basis for agreement negotiations and ultimately for a signed Agreement with the selected Bidders. |
|  | - Bidders should familiarize themselves with assignment conditions and take them into account in preparing their Proposals. To obtain first-hand information on the assignment, Bidders are encouraged to visit the Client before submitting a proposal and to attend a pre-proposal conference as specified in the Data Sheet. Attending the pre-proposal conference will be optional. Bidders should contact the Client’s representative named in the Data Sheet to obtain additional information on the pre-proposal conference. Bidders should ensure these officials are informed well-ahead of time in case they wish to visit the Client. |
|  | - The Client will timely provide at no cost to the Bidders the inputs and facilities specified in the Data Sheet, assist the firm in obtaining licenses and permits needed to carry out the services, and make available relevant project data and reports. - Bidders shall bear all costs associated with the preparation and submission of their proposals and agreement negotiation. The Client is not bound to accept any proposal, and reserves the right to annul the selection process at any time prior to Agreement award, without thereby incurring any liability to the Bidders. |
| Conflict of Interest | - Government of Punjab policy requires that Bidders provide professional, objective, and impartial advice and at all times hold the Client’s interests paramount, strictly avoid conflicts with other assignments or their own corporate interests and act without any consideration for future work. - Without limitation on the generality of the foregoing, Bidders, and any of their affiliates, shall be considered to have a conflict of interest and shall not be recruited, under any of the circumstances set forth below: |
| Conflicting activities | - A firm/consortium that has been engaged by the Client to provide goods, works or services other than consulting services for a project, and any of its affiliates, shall be disqualified from providing consulting services related to those goods, works or services. Conversely, a firm/consortium hired to provide consulting services for the preparation or implementation of a project, and any of its affiliates, shall be disqualified from subsequently providing goods or works or services other than consulting services resulting from or directly related to the firm’s consulting services for such preparation or implementation. For the purpose of this paragraph, services other than consulting services are defined as those leading to a measurable physical output, for example surveys, aerial photography, and satellite imagery. |
| Conflicting assignments | - A Bidder (including its Personnel and Sub-Consultants) or any of its affiliates shall not be hired for any assignment that, by its nature, may be in conflict with another assignment of the Bidder to be executed for the same or for another Client. For example, a Bidder hired to prepare engineering design for an infrastructure project shall not be engaged to prepare an independent environmental assessment for the same project, and a Bidder assisting a Client in the privatization of public assets shall not purchase, nor advice purchasers of, such assets. Similarly, a Bidder hired to prepare Terms of Reference for an assignment should not be hired for the assignment in question. |
| Conflicting relationships | - A Bidder (including its Personnel and Sub-Consultants) that has a business or family relationship with a member of the Client’s staff who is directly or indirectly involved in any part of (i) the preparation of the Terms of Reference of the assignment, (ii) the selection process for such assignment, or (iii) supervision of the Agreement, may not be awarded an Agreement, unless the conflict stemming from this relationship has been resolved in a manner acceptable to the Government of Punjab throughout the selection process and the execution of the Agreement. |
|  | - Bidder have an obligation to disclose any situation of actual or potential conflict that impacts their capacity to serve the best interest of their Client, or that may reasonably be perceived as having this effect. Failure to disclose said situations may lead to the disqualification of the Bidder or the termination of its Agreement. - No agency or current employees of the Client shall work as Bidder under their own ministries, departments or agencies. Recruiting former government employees of the Client to work for their former ministries, departments or agencies is acceptable provided no conflict of interest exists. When the Bidder nominates any government employee as Personnel in their technical proposal, such Personnel must have written certification from their government or employer confirming that they are on leave without pay from their official position and allowed to work full-time outside of their previous official position. Such certification shall be provided to the Client by the Bidder as part of his technical proposal. |
| Unfair Advantage | - If a shortlisted Bidder could derive a competitive advantage from having provided consulting services related to the assignment in question, the Client shall make available to all shortlisted Bidders together with this RFP all information that would in that respect give such Bidder any competitive advantage over competing Bidders. |
| Fraud and Corruption | - The Government of Punjab requires Bidders participating in its projects to adhere to the highest ethical standards, both during the selection process and throughout the execution of an agreement. In pursuance of this policy, the Government of Punjab: - defines, for the purpose of this paragraph, the terms set forth below as follows: - “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of a public official in the selection process or in agreement execution; - “fraudulent practice” means a misrepresentation or omission of facts in order to influence a selection process or the execution of a agreement; - “collusive practices” means a scheme or arrangement between two or more Bidders with or without the knowledge of the Client, designed to establish prices at artificial, noncompetitive levels; - “coercive practices” means harming or threatening to harm, directly or indirectly, persons or their property to influence their participation in a procurement process, or affect the execution of an agreement. - will reject a proposal for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the agreement in question; - will sanction a Bidder, including declaring the Bidder ineligible, either indefinitely or for a stated period of time, to be awarded a Government of Punjab agreement if at any time it determines that the Bidder has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, a Government of Punjab agreement; and - will have the right to require that a provision be included requiring Bidders to permit the Government of Punjab to inspect their accounts and records and other documents relating to the submission of proposals and agreement performance, and have them audited by auditors appointed by the Government of Punjab. |
|  | - Bidders, their Sub-Bidders, and their associates shall not be under a declaration of ineligibility for corrupt and fraudulent practices issued by the Government of Punjab in accordance with the above para. 1.7. Furthermore, the Bidders shall be aware of the provisions on fraud and corruption stated in the specific clauses in the General Conditions of Agreement. - Bidders shall furnish information on commissions and gratuities, if any, paid or to be paid to agents relating to this proposal and during execution of the assignment if the Bidder is awarded the Agreement, as requested in the Financial Proposal submission form (Section 4). |
| Only one Proposal | - Bidders may submit only one proposal. If a Bidder submits or participates in more than one proposal, such proposals shall be disqualified. |
| Proposal Validity | - The Data Sheet indicates how long Bidder’s Proposals must remain valid after the submission date. During this period, Bidders shall maintain the availability of Professional staff nominated in the Proposal. The Client will make its best effort to complete negotiations within this period. Should the need arise, however, the Client may request Bidders to extend the validity period of their proposals. Bidders who agree to such extension shall confirm that they maintain the availability of the Professional staff nominated in the Proposal, or in their confirmation of extension of validity of the Proposal, Bidders could submit new staff in replacement, who would be considered in the final evaluation for agreement award. Bidders who do not agree have the right to refuse to extend the validity of their Proposals. |
| Eligibility of Sub-Consultants | - In case a Bidder intends to associate with Bidders who have not been issued LOI and/or individual expert(s), such other Bidders and/or individual expert(s) shall be subject to the eligibility criteria set forth in the Guidelines. |
| - Clarification and Amendment of RFP Documents | - Bidders may request clarification of any of the RFP documents up to the number of days indicated in the Data Sheet before the proposal submission date. Any request for clarification must be sent in writing, or by standard electronic means to the Client’s address indicated in the Data Sheet. The Client will respond in writing, or by standard electronic means and will send written copies of the response (including an explanation of the query but without identifying the source of inquiry) to all Bidders. Should the Client deem it necessary to amend the RFP as a result of a clarification, it shall do so following the procedure under para. 2.2. - At any time before the submission of Proposals, the Client may amend the RFP by issuing an addendum in writing or by standard electronic means. The addendum shall be sent to all Bidders and will be binding on them. Bidders shall acknowledge receipt of all amendments. To give Bidders reasonable time in which to take an amendment into account in their Proposals the Client may, if the amendment is substantial, extend the deadline for the submission of Proposals. |
| - Preparation of Proposals | - The Proposal (see para. 1.2), as well as all related correspondence exchanged by the Bidders and the Client, shall be written in the language (s) specified in the Data Sheet. |
|  | - In preparing their Proposal, Bidders are expected to examine in detail the documents comprising the RFP. Material deficiencies in providing the information requested may result in rejection of a Proposal. |
|  | - While preparing the Technical Proposal, Bidders must give particular attention to the following: - If a Bidder considers that it may enhance its expertise for the assignment by associating with other Bidders in a joint venture or sub-consultancy, it may associate with either Bidders, if so indicated in the Data Sheet. A Consultant must first obtain the approval of the Client if it wishes to enter into a joint venture with any other Bidder. In case of association with other Bidder(s), the Bidder shall act as association leader. Any association must be clearly indicated in the technical proposal. In case of a joint venture, all partners shall be jointly and severally liable and shall indicate who will act as the leader of the joint venture. |
|  | - Alternative professional staff shall not be proposed, and only one curriculum vitae (CV) may be submitted for each position. |
| Technical Proposal Format and Content | - The Technical Proposal shall provide the information indicated in the following paras from (a) to (g) using the attached Standard Forms (Section 3). Paragraph (c) (ii) indicates the recommended number of pages for the description of the approach, methodology and work plan of the Technical Proposal. A page is considered to be one printed side of A4 or letter size paper. |
|  | - A brief description of the Consultants’ organization and an outline of recent experience of the Consultants (each partner in case of joint venture) on assignments of a similar nature is required in Form TECH-2 of Section 3. For each assignment, the outline should indicate the names of Sub-Consultants/ Professional staff who participated, duration of the assignment, agreement amount, and Consultant’s involvement. Information should be provided only for those assignments for which the Consultant was legally engaged by the Client as a firm or as one of the major firms within a joint venture. Assignments completed by individual Professional staff working privately or through other consulting firms cannot be claimed as the experience of the Consultant, or that of the Consultant’s associates, but can be claimed by the Professional staff themselves in their CVs. Consultants should be prepared to substantiate the claimed experience if so requested by the Client. - Comments and suggestions on the Terms of Reference including workable suggestions that could improve the quality/ effectiveness of the assignment; and on requirements for counterpart staff and facilities including: administrative support, office space, local transportation, equipment, data, etc. to be provided by the Client (Form TECH-3 of Section 3). - A description of the approach, methodology and work plan for performing the assignment covering the following subjects: technical approach and methodology, work plan, and organization and staffing schedule. Guidance on the content of this section of the Technical Proposals is provided under Form TECH-4 of Section 3. The work plan should be consistent with the Work Schedule (Form TECH-8 of Section 3) which will show in the form of a bar chart the timing proposed for each activity. - The list of the proposed Professional staff team by area of expertise, the position that would be assigned to each staff team member, and their tasks (Form TECH-5 of Section 3). - Estimates of the staff input (staff-months of foreign and local professionals) needed to carry out the assignment (Form TECH-7 of Section 3). The staff-months input should be indicated separately for home office and field activities, and for foreign and local Professional staff. - CVs of the Professional staff signed by the staff themselves or by the authorized representative of the Professional Staff (Form TECH-6 of Section 3) along with their Computerized National Identity Card numbers (if local) or Passport numbers (if foreign). - A detailed description of the proposed methodology and staffing for training, if the Data Sheet specifies training as a specific component of the assignment. |
|  | - The Technical Proposal shall not include any financial information. A Technical Proposal containing financial information is liable to be declared non responsive. |
| Financial Proposals | - The Financial Proposal shall be prepared using the attached Standard Forms (Section 4). It shall list all costs associated with the assignment, including (a) remuneration for staff (foreign and local, in the field and at the Bidder’s home office), and (b) reimbursable expenses indicated in the Data Sheet. If appropriate, these costs should be broken down by activity and, if appropriate, into foreign and local expenditures. All activities and items described in the Technical Proposal must be priced separately; activities and items described in the Technical Proposal but not priced, shall be assumed to be included in the prices of other activities or items. |
| Taxes | - The Bidders will be subject to local taxes (such as: value added or sales tax or income taxes on non-resident Foreign Personnel, duties, fees, levies) on amounts payable by the Client under the Agreement. Any such amounts shall be included in the Financial Proposal as they will be evaluated, but they will be discussed at agreement negotiations, and applicable amounts will be included in the Agreement. |
|  | - Bidders should express the price of their services in Pakistan Rupees. Prices in other currencies should be converted to Pakistan Rupees using the selling rates of exchange given by the State Bank of Pakistan for the date indicated in the Data Sheet. - Commissions and gratuities, if any, paid or to be paid by Bidders and related to the assignment will be listed in the Financial Proposal Form FIN-1 of Section 4. |
| - Submission, Receipt, and Opening of Proposals | - The original proposal (Technical Proposal and, if required, Financial Proposal; see para. 1.2) shall contain no interlineations or overwriting, except as necessary to correct errors made by the Bidders themselves. The person who signed the proposal must initial such corrections. Submission letters for both Technical and Financial Proposals should respectively be in the format of TECH-1 of Section 3, and FIN-1 of Section 4. - An authorized representative of the Bidders shall initial all pages of the original Technical and Financial Proposals. The authorization shall be in the form of a written power of attorney accompanying the Proposal or in any other form demonstrating that the representative has been duly authorized to sign. The signed Technical and Financial Proposals shall be marked “Original”. - The Technical Proposal shall be marked “Original” or “Copy” as appropriate. The Technical Proposals shall be sent to the addresses referred to in para. 4.5 and in the number of copies indicated in the Data Sheet. All required copies of the Technical Proposal are to be made from the original. If there are discrepancies between the original and the copies of the Technical Proposal, the original governs. - The original and two copies of the Technical Proposal shall be placed in a sealed envelope clearly marked “Technical Proposal”. Similarly, the original Financial Proposal shall be placed in a sealed envelope clearly marked “Financial Proposal” followed by the name of the assignment, and with a warning “Do Not Open With The Technical Proposal.” The envelopes containing the Technical and Financial Proposals shall be placed into an outer envelope and sealed. This outer envelope shall bear the submission address and title of the Assignment, clearly marked “Do Not Open, Except In Presence Of The Official Appointed, Before Submission Deadline”. The Client shall not be responsible for misplacement, losing or premature opening if the outer envelope is not sealed and/or marked as stipulated. This circumstance may be case for Proposal rejection. If the Financial Proposal is not submitted in a separate sealed envelope duly marked as indicated above, this will constitute grounds for declaring the Proposal non-responsive. |
|  | - The Proposals must be sent to the address/addresses indicated in the Data Sheet and received by the Client no later than the time and the date indicated in the Data Sheet, or any extension to this date in accordance with para. 2.2. Any proposal received by the Client after the deadline for submission shall be returned unopened. - The Client shall open the Technical Proposal immediately after the deadline for their submission. The envelopes with the Financial Proposal shall remain sealed and securely stored. |
| - Proposal Evaluation | - From the time the Proposals are opened to the time the Agreement is awarded, the Consultants should not contact the Client on any matter related to its Technical and/or Financial Proposal. Any effort by Consultants to influence the Client in the examination, evaluation, ranking of Proposals, and recommendation for award of Agreement may result in the rejection of the Bidders’ Proposal. Evaluators of Technical Proposals shall have no access to the Financial Proposals until the technical evaluation is concluded. |
| Evaluation of Technical Proposals | - The evaluation committee shall evaluate the Technical Proposals on the basis of their responsiveness to the Terms of Reference, applying the evaluation criteria, sub-criteria, and point system specified in the Data Sheet. Each responsive Proposal will be given a technical score (St). A Proposal shall be rejected at this stage if it does not respond to important aspects of the RFP, and particularly the Terms of Reference or if it fails to achieve the minimum technical score indicated in the Data Sheet. |
| Public Opening and Evaluation of Financial Proposals (only for QCBS, Fixed Budget Selection, and Least-Cost Selection) | - After the technical evaluation is completed, the Client shall inform the Bidders who have submitted proposals the technical scores obtained by their Technical Proposals, and shall notify those Bidders whose Proposals did not meet the minimum qualifying mark or were considered non responsive to the RFP and TOR, that their Financial Proposals will be returned unopened after completing the selection process. The Client shall simultaneously notify in writing Bidders that have secured the minimum qualifying mark, the date, time and location for opening the Financial Proposals. Bidders’ attendance at the opening of Financial Proposals is optional. The opening date shall be set so as to allow interested Bidders sufficient time to make arrangements for attending the opening. - Financial Proposals shall be opened publicly in the presence of the Bidders’ representatives who choose to attend. The name of the Bidders and the technical scores of the Bidders shall be read aloud. The Financial Proposal of the Bidders who met the minimum qualifying mark will then be inspected to confirm that they have remained sealed and unopened. These Financial Proposals shall be then opened, and the total prices read a loud and recorded. - The Evaluation Committee will correct any computational errors. When correcting computational errors, in case of discrepancy between a partial amount and the total amount, or between word and figures, the formers will prevail. In addition to the above corrections, as indicated under para. 3.6, activities and items described in the Technical Proposal but not priced, shall be assumed to be included in the prices of other activities or items. In case an activity or line item is quantified in the Financial Proposal differently from the Technical Proposal, the Evaluation Committee shall correct the quantification indicated in the Financial Proposal so as to make it consistent with the Technical Proposal, apply the relevant unit price included in the Financial Proposal. - As required in the QCBS method, the lowest evaluated Financial Proposal (Fm) will be given the maximum financial score (Sf) of 100 points. The financial scores (Sf) of the other Financial Proposals will be computed as indicated in the Data Sheet. Proposals will be ranked according to their combined technical (St) and financial (Sf) scores using the weights (T = the weight given to the Technical Proposal; P = the weight given to the Financial Proposal; T + P = 1) indicated in the Data Sheet: S = St x T% + Sf x P%. The firm achieving the highest combined technical and financial score will be invited for negotiations. |
| - Negotiations | - Negotiations will be held at the date and address indicated in the Data Sheet. The invited Bidder will, as a pre-requisite for attendance at the negotiations, confirm availability of all Professional staff. Failure in satisfying such requirements may result in the Client proceeding to negotiate with the next-ranked Consultant. Representatives conducting negotiations on behalf of the Bidder must have written authority to negotiate and conclude an Agreement. |
| Technical negotiations | - Negotiations will include a discussion of the Technical Proposal, the proposed technical approach and methodology, work plan, and organization and staffing, and any suggestions made by the Bidder to improve the Terms of Reference. The Client and the Bidders will finalize the Terms of Reference, staffing schedule, work schedule, logistics, and reporting. These documents will then be incorporated in the Agreement as “Description of Services”. Special attention will be paid to clearly defining the inputs and facilities required from the Client to ensure satisfactory implementation of the assignment. The Client shall prepare minutes of negotiations which will be signed by the Client and the Bidder. |
| Financial negotiations | - If applicable, it is the responsibility of the Bidder, before starting financial negotiations, to determine the tax amount to be paid by the Bidder under the Agreement. The financial negotiations will reflect the agreed technical modifications in the cost of the services. As required in the QCBS method, financial negotiations can involve the remuneration rates for staff or other proposed unit rates if there is a revision of scope or if the bid rate exceeds the available budget. For other methods, Bidders will provide the Client with the information on remuneration rates described in the Appendix attached to Section 4 – Financial Proposal - Standard Forms of this RFP. |
| Availability of Professional staff/experts | - Having selected the Bidder on the basis of, among other things, an evaluation of proposed Professional staff, the Client expects to negotiate an Agreement on the basis of the Professional staff named in the Proposal. Before agreement negotiations, the Client will require assurances that the Professional staff will be actually available. The Client will not consider substitutions during agreement negotiations unless both parties agree that undue delay in the selection process makes such substitution unavoidable or for reasons such as death or medical incapacity. If this is not the case and if it is established that Professional staff were offered in the proposal without confirming their availability, the Bidder may be disqualified. Any proposed substitute shall have equivalent or better qualifications and experience than the original candidate and be submitted by the Bidder within the period of time specified in the letter of invitation to negotiate. |
| Conclusion of the negotiations | - Negotiations will conclude with a review of the draft Agreement. To complete negotiations the Client and the Bidder will initial the agreed Agreement. If negotiations fail, the Client will invite the Bidder whose Proposal received the second highest score to negotiate an Agreement. |
| - Award of Agreement | - After completing negotiations the Client shall award the Agreement to the selected Bidder and publish details on the LDA’s website and promptly notify all Bidders who have submitted proposals. After Agreement signature, the Client shall return the unopened Financial Proposals to the unsuccessful Bidders. - The Bidder is expected to commence the assignment on the date and at the location specified in the Data Sheet. |
| - Confidentiality | - Information relating to evaluation of Proposals and recommendations concerning awards shall not be disclosed to the Bidders who submitted the Proposals or to other persons not officially concerned with the process, until the publication of the award of Agreement. The undue use by any Bidder of confidential information related to the process may result in the rejection of its Proposal and may be subject to the provisions of the Bidder Selection Guidelines relating to fraud and corruption. |

### Instructions to Bidders

## Data Sheet

| Paragraph Reference |  |
| --- | --- |
| ### 1.1 | Name of the Client: Lahore Development Authority (LDA) Method of selection: Quality and Cost Based Selection (QCBS) as per Consultants Selection Guidelines of P&D Board, Government of the Punjab. |
| 1.2 | Financial Proposal to be submitted together with Technical Proposal: Yes Name of the assignment is: “Integrated Strategic Development Plan for Lahore Region 2035 (ISDP-35)”. |
| 1.3 | A pre-proposal conference will be held: Yes, on July 16, 2013 at 2:00 pm at 467-DII Johar Town, Lahore or at any other date and time mutually agreed, but not later than July 18, 2013. The Client’s representative is: WASEEM AHMAD KHAN Address: 467 – DII Johar Town, LDA, Lahore Telephone: +92-42-99262332 Facsimile: Fax No: +92-42-99262373 E-mail: cmpwinglda@gmail.com info.isdp35@gmail.com |
| 1.4 | The Client will provide the following inputs and facilities: a):Available relevant information / data. b):The client will provide office premises with furniture and power backup for both consultants’ team and counterpart team from the clients’ side for facilitation, coordination, as well as capacity and technology transfer. |
| 1.6.1 (a) | The Client envisages the need for continuity for downstream work: No |
| 1.12 | Proposals must remain valid for 90 days after the submission date. |
| 2.1 | Clarifications may be requested not later than July 24, 2013. The address for requesting clarifications is: Facsimile: +92-42-99262373 E-mail: cmpwinglda@gmail.com, info.isdp35@gmail.com |
| 3.1 | Proposals shall be submitted in the following language: English |
| 3.3 (a) | Consultants may associate with other Consultants: Yes |
| 3.3 (b) | The Financial Proposal shall not exceed the available budget of: Rs 200,000,000. (Pak Rupees Two Hundred Millions) (All payments will be made in Pak Rupees. However, if a bidder forms consortia with a foreign firm, then 20% of total cost in Pak Rupees may be released in dollars by apply the current exchange rate ) |
| 3.4 (a) | Consultant should submit details of five most relevant assignments, performed during the last ten years. |
| 3.4 (f) | CVs of the key personnel to be working on this assignment should contain details of Five projects done by the individual in the past. |
| 3.4 (g) | Training is a specific component of this assignment: Yes |
| 3.6 | List of the applicable Reimbursable expenses in local currency; - Cost of surveys; - Cost of applicable or local communications such as the use of telephone and facsimile required for the purpose of the Services; - Cost, rental and freight of any instruments or equipment required to be provided by the Consultants for the purposes of the Services; - Cost of printing and dispatching of the reports to be produced for the Services; The above reimbursable expenses will be considered as direct cost(s) but will be payable to the consultant, as per actual. |
| 3.7 | Amounts payable by the Client to the Consultant under the agreement to be subject to local taxation: Yes |
| 3.8 | The Consultant should state the cost in financial proposal in Pak Rupees. |
| 4.3 | Consultant must submit one original and two copies of the Technical Proposal, and the original & on copy of the Financial Proposal. |
| 4.5 | The Proposal submission address is: WASEEM AHMAD KHAN, Chief Metropolitan Planner, 467 – DII Johar Town, LDA, Lahore Proposals must be submitted not later than the following date and time: By July 31, 2013 up to 3:00 pm. |
| 5.2 (a) | Criteria, sub-criteria, and point system for the evaluation of Technical Proposals are:- Points (i) Company Profile: [100] a) Number of similar assignments [45] b) Value of similar assignments [45] c) Organizational structure [10] ___ Total = A1 (ii) Project Team: [100] - Team Leader (Strategic Development Expert in Urban Strategic Development Planning); 20. - Urban Planner; 10. - Urban Economist; 10. - Traffic and Transportation Expert; 10. - Financial Analyst; 10. - Institutional Development Specialist; 10. - Municipal Services (Water & Sanitation & Solid Waste Management) expert; 10. - Urban Environmentalist; 10. - Urban / Public Space Management Expert / Urban Designer / Landscapist / Horticulturist; 10. Total = A2 The number of points to be assigned to each of the above positions or disciplines shall be determined considering the following three sub-criteria and relevant score: 1) Education and qualifications [25] 2) Relevant experience [70] 3) Time with firm [5] ___ Total score: 100 (iii) Approach & Methodology: [100] a) Understanding & Innovativeness [40] b) Methodology & Work plan [40] c) Capacity & Technology Transfer component [20] ___ Total = A3 Technical Score* =; A1[0.10]; +; A2[0.50]; +; A3[0.40]. 100; 100; 100. The minimum technical score St required to pass is: 65 - Points. |
| 5.7 | The formula for determining the financial scores is the following: Sf = 100 x Fm / F, in which Sf is the financial score, Fm is the lowest price and F the price of the proposal under consideration. The weights given to the Technical (T) and Financial Proposals (F) are: T = 0.80 P = 0.20 |
| 6.1 | Expected date and address for agreement negotiations: 4th week of August 2013 at 467 – DII Johar Town, LDA, Lahore. |
| 7.2 | Expected date for commencement of consulting services 4th Week of August 2013 at Lahore. |

# SECTION 3: TECHNICAL PROPOSAL - STANDARD FORMS

Refer to Reference Paragraph 3.4 of the Data Sheet for format of Technical Proposal to be submitted, and paragraph 3.4 of Section 2 of the RFP for Standard Forms required and number of pages recommended.

TECH-1	Technical Proposal Submission Form

TECH-2	Consultant’s Organization and Experience

A	Consultant’s Organization

B	Consultant’s Experience

TECH-3	Comments or Suggestions on the Terms of Reference and on Counterpart Staff and Facilities to be provided by the Client

A	On the Terms of Reference

B	On the Counterpart Staff and Facilities

TECH-4	Description of the Approach, Methodology and Work Plan for Performing the Assignment

TECH-5	Team Composition and Task Assignments

TECH-6	Curriculum Vitae (CV) for Proposed Professional Staff

TECH-7	Staffing Schedule

TECH-8	Work Schedule

### FORM  TECH-1  TECHNICAL PROPOSAL SUBMISSION FORM

[Location, Date]

To:	[Name and address of Client]

Dear Sir,

We, the undersigned, offer to provide the consulting services for [Insert title of assignment] in accordance with your Request for Proposal dated [Insert Date]. We are hereby submitting Proposal, which includes the Technical Proposal, and a Financial Proposal sealed under separate envelopes1.

We are submitting Proposal in association with: [Insert a list with full name and address of each associated Consultant if any]2

We hereby declare that all the information and statements made in this Proposal are true and accept that any misinterpretation contained in it may lead to our disqualification.

If negotiations are held during the period of validity of the Proposal, i.e., before the date indicated in Paragraph Reference 1.12 of the Data Sheet, we undertake to negotiate on the basis of the proposed staff.  This Proposal is binding upon us and subject to the modifications resulting from Agreement negotiations.

We undertake, if the Proposal is accepted, to initiate the consulting services related to the assignment not later than the date indicated in Paragraph Reference 7.2 of the Data Sheet.

We understand you are not bound to accept any Proposal you receive.

We remain,

Yours sincerely,

Authorized Signature [In full and initials]:

Name and Title of Signatory:

Name of Firm:

Address:

1	[In case Paragraph Reference 1.2 of the Data Sheet requires to submit a Technical Proposal only, replace this sentence with: “We are hereby submitting our Proposal, which includes this Technical Proposal only.”]

2	[Delete in case no association is foreseen.]

### FORM  TECH-2  CONSULTANT’S ORGANIZATION AND EXPERIENCE

#### A - Consultant’s Organization

[Provide here a brief (two pages) description of the background and organization of your firm/entity (including organogram) and each associate for this assignment.]

- Firm Background:

- Chief Executive Officer:

- Board of Directors / Partners.

- Departmental Structure of the Firm

- Organogram

A-I

Whether your Firm is ISO Certified? If so provide a copy of ISO Certification.

B - Consultant’s Experience

[Using the format below, provide information on each assignment for which your firm, and each associate for this assignment, was legally contracted as a corporate entity or as one of the major companies within an association, for carrying out consulting services similar to the ones requested under this Assignment. Use maximum 20 pages. Please provide Client’s certification and/or evidence of the contract agreement.]

| Assignment name: | Value of agreement (in current PKR) |
| --- | --- |
| Country: Location within country: | Duration of project (months): |
| Name of Client: | Total No of staff-months (by your firm) on the project: |
| Start date (month/year): Completion date (month/year): | Value of total project provided under an agreement (in current PKR) In case of consortium, value of part of the project provided by bidder under the agreement (in current PKR) |
| Name of associated members, if any: | No of professional staff-months provided by associated members: |
| Name of senior professional staff of your firm involved and functions performed (indicate most significant profiles such as Team Leader, Urban Economist etc) |  |
| Narrative description of Project: |  |
| Description of actual services provided by your staff within the assignment |  |
| 1. Firms Name: …………………………… 2. Certificate by the Client / Employer that the work was successfully completed by the consultant. |  |

### Form  TECH-3  Comments and Suggestions on the Terms of Reference and on Counterpart Staff and Facilities to be Provided by the Client

#### A - On the Terms of Reference

[Present and justify here any modifications or improvement to the Terms of Reference you are proposing to improve performance in carrying out the assignment (such as deleting some activity you consider unnecessary, or adding another, or proposing a different phasing of the activities).  Such suggestions should be concise and to the point, and incorporated in your Proposal.]

#### B - On Counterpart Staff and Facilities

[Comment here on counterpart staff and facilities to be provided by the Client according to Paragraph Reference 1.4 of the Data Sheet including: administrative support, office space, local transportation, equipment, data, etc.]

### FORM  TECH-4	DESCRIPTION OF APPROACH, METHODOLOGY AND WORK PLAN FOR PERFORMING THE ASSIGNMENT

[Technical approach, methodology and work plan are key components of the Technical Proposal.  You are suggested to present your Technical Proposal (50 pages, inclusive of charts and diagrams) divided into the following three chapters:

- Technical Approach and Methodology,

- Work Plan, and

- Organization and Staffing,

- Technical Approach and Methodology.  In this chapter you should explain your understanding of the objectives of the assignment, approach to the services, methodology for carrying out the activities and obtaining the expected output, and the degree of detail of such output. You should highlight the problems being addressed and their importance, and explain the technical approach you would adopt to address them. You should also explain the methodologies you propose to adopt and highlight the compatibility of those methodologies with the proposed approach.

- Work Plan.  In this chapter you should propose the main activities of the assignment, their content and duration, phasing and interrelations, milestones (including interim approvals by the Client), and delivery dates of the reports. The proposed work plan should be consistent with the technical approach and methodology, showing understanding of the TOR and ability to translate them into a feasible working plan. A list of the final documents, including reports, drawings, and tables to be delivered as final output, should be included here. The work plan should be consistent with the Work Schedule of Form TECH-8.

- Organization and Staffing.  In this chapter you should propose the structure and composition of your team. You should list the main disciplines of the assignment, the key expert responsible, and proposed technical and support staff.]

### FORM  TECH-5  TEAM COMPOSITION AND TASK ASSIGNMENTS

| Professional Staff |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of Staff | CNIC No./Passport No. | Firm | Area of Expertise | Position Assigned | Task Assigned |

### FORM  TECH-6	CURRICULUM VITAE (CV) FOR PROPOSED PROFESSIONAL STAFF

- Proposed Position [only one candidate shall be nominated for each position]:

- Name of Firm [Insert name of firm proposing the staff]:

- Name of Staff [Insert full name]:

- Date of Birth:  	 Nationality:

- CNIC No (if Pakistani): 	 or Passport No:

- Education :

| Degree | Major/Minor | Institution | Date (MM/YYYY) |
| --- | --- | --- | --- |

- Membership of Professional Associations:

- Other Training  [Indicate significant training since degrees under 6 - Education were obtained]:

- Languages [For each language indicate proficiency: good, fair, or poor in speaking, reading, and writing]:

- Employment Record  [Starting with present position, list in reverse order every employment held by staff member since graduation, giving for each employment (see format here below): dates of employment, name of employing organization, positions held.]:

| Employer | Position | From (MM/YYYY) | To (MM/YYYY) |
| --- | --- | --- | --- |

11. Detailed Tasks Assigned [List all tasks to be performed under this assignment]

12. Work Undertaken that Best Illustrates Capability to Handle the Tasks Assigned [Among the assignments in which the staff has been involved, indicate the following information for those assignments that best illustrate staff capability to handle the tasks listed under point 11.] - Name of assignment or project & Location: ____________ Cost of Project__________ Date of Start________________ Date of Completion __________________________ Actual Time Spent on the Project: ____________________________ in months. Client: Main project features: Positions held: Activities performed: 2) Name of assignment or project: Year: _________________________ -do- ______________________________ Location: Client: Main project features: Positions held: Activities performed: 3) Name of assignment or project: Year: __________________________ -do- ______________________________ Location: Client: Main project features: Positions held: Activities performed: [Unroll the project details group and continue numbering (4, 5, …) as many times as is required]

13.	Certification:

I, the undersigned, certify that to the best of my knowledge and belief, this CV correctly describes me, my qualifications, and my experience.  I understand that any wilful misstatement described herein may lead to my disqualification or dismissal, if engaged.

Date:

[Signature of staff member or authorized representative of the staff]	Day/Month/Year

Full name of authorized representative:

### FORM  TECH-7  STAFFING SCHEDULE1

Full time input

Part time input

| Year: __________ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### N° | Name of Staff | ### Staff input (in the form of a bar chart)2 |  |  |  |  |  |  |  |  |  |  |  | ### Total staff-month input |  |  |
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Home | Field3 | Total |
| Foreign |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  | [Home] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | [Field] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| n |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal |  |  |  |  |  |
| Local |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  | [Home] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | [Field] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| n |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total |  |  |  |  |  |

1	For Professional Staff the input should be indicated individually; for Support Staff it should be indicated by category (e.g.: draftsmen, clerical staff, etc.).

2	Months are counted from the start of the assignment.  For each staff indicate separately staff input for home and field work.

3	Field work means work carried out at a place other than the Consultant's home office.

### FORM  TECH-8  WORK SCHEDULE

|  | Year: __________ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N° | Activity1 |  | Months2 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1	Indicate all main activities of the assignment, including delivery of reports (e.g.: inception, interim, and final reports), and other benchmarks such as Client approvals.  For phased assignments indicate activities, delivery of reports, and benchmarks separately for each phase.

2	Duration of activities shall be indicated in the form of a bar chart.

# SECTION 4:  FINANCIAL PROPOSAL - STANDARD FORMS

[Comments in brackets [  ] provide guidance to the shortlisted Consultants for the preparation of their Financial Proposals; they should not appear on the Financial Proposals to be submitted.]

Financial Proposal Standard Forms shall be used for the preparation of the Financial Proposal according to the instructions provided under para. 3.6 of Section 2.  Such Forms are to be used whichever is the selection method indicated in para. 4 of the Letter of Invitation.

[The Appendix “Financial Negotiations - Breakdown of Remuneration Rates” is to be only used for financial negotiations when Quality-Based Selection, Selection Based on Qualifications, or Single-Source Selection method is adopted, according to the indications provided under para. 6.3 of Section 2.]

FIN-1	Financial Proposal Submission Form

FIN-2	Summary of Costs

FIN-3	Breakdown of Costs by Activity

FIN-4	Breakdown of Remuneration

FIN-5	Reimbursable expenses

Appendix:	Financial Negotiations - Breakdown of Remuneration Rates

### FORM  FIN-1  FINANCIAL PROPOSAL SUBMISSION FORM

[Location, Date]

To:	[Name and address of Client]

Dear Sir,

We, the undersigned, offer to provide the consulting services for [Insert title of assignment] in accordance with your Request for Proposal dated [Insert Date] and our Technical Proposal.  Our attached Financial Proposal is for the sum of [Insert amount(s) in words and figures1].  This amount is inclusive of the taxes and taxes are separately indicated in the Proposal.

Our Financial Proposal shall be binding upon us subject to the modifications resulting from Agreement negotiations, up to expiration of the validity period of the Proposal, i.e. before the date indicated in Paragraph Reference 1.12 of the Data Sheet.

No commissions or gratuities have been or are to be paid by us to agents relating to this Proposal and Agreement execution.

We understand you are not bound to accept any Proposal you receive.

We remain,

Yours sincerely,

Authorized Signature [In full and initials]:

Name and Title of Signatory:

Name of Firm:

Address:

### FORM  FIN-2  SUMMARY OF COSTS

| - Item | Costs |
| --- | --- |
| Total Costs of Financial Proposal | (Pak Rs. ) |

### FORM  FIN-3  BREAKDOWN OF COSTS BY ACTIVITY1

| Group of Activities (Phase):2 | Description:3 |  |
| --- | --- | --- |
| Cost component | Costs (Pak Rupees) |  |
| Remuneration4 |  |  |
| Reimbursable Expenses 4 |  |  |
| Subtotals |  |  |

1	Form FIN-3 shall be filled at least for the whole assignment.  In case some of the activities require different modes of billing and payment (e.g.: the assignment is phased, and each phase has a different payment schedule), the Consultant shall fill a separate Form FIN-3 for each group of activities.  The sum of the relevant Subtotals of all Forms FIN-3 provided must coincide with the Total Costs of Financial Proposal indicated in Form FIN-2.

2	Names of activities (phase) should be the same as, or correspond to the ones indicated in the second column of Form TECH-8.

3	Short description of the activities whose cost breakdown is provided in this Form.

4	 Remuneration and Reimbursable Expenses must respectively coincide with relevant Total Costs indicated in Forms FIN-4, and FIN-5.

### FORM  FIN-4  BREAKDOWN OF REMUNERATION1

(This Form FIN-4 shall only be used when the Lump-Sum Form of Agreement has been included in the RFP.  Information to be provided in this Form shall only be used to establish payments to the Bidder for possible additional services requested by the Client)

| Name2 | Position3 | Staff-month Rate4 |
| --- | --- | --- |
| Local Staff |  |  |
|  |  | [Home] |
|  |  | [Field] |
| Foreign Staff |  |  |
|  |  | [Home] |
|  |  | [Field] |

1	Form FIN-4 shall be filled in for the same Professional and Support Staff listed in Form TECH-7.

2	Professional Staff should be indicated individually; Support Staff should be indicated per category (e.g.: draftsmen, clerical staff).

3	Positions of the Professional Staff shall coincide with the ones indicated in Form TECH-5.

4	Indicate separately staff-month rate and rate  for home and field work.

### FORM  FIN-5  BREAKDOWN OF REIMBURSABLE EXPENSES

(This Form FIN-5 shall only be used when the Lump-Sum Form of Agreement has been included in the RFP.  Information to be provided in this Form shall only be used to establish payments to the Bidder for possible additional services requested by the Client)

| N° | Description1 | Unit | Unit Cost2 |
| --- | --- | --- | --- |
|  | Per diem allowances | Day |  |
|  | International flights3 | Trip |  |
|  | Miscellaneous travel expenses | Trip |  |
|  | Communication costs between [Insert place] and [Insert place] |  |  |
|  | Drafting, reproduction of reports |  |  |
|  | Equipment, instruments, materials, supplies, etc. |  |  |
|  | Shipment of personal effects | Trip |  |
|  | Use of computers, software |  |  |
|  | Laboratory tests. |  |  |
|  | Sub-agreements |  |  |
|  | Local transportation costs |  |  |
|  | Office rent, clerical assistance |  |  |
|  | Training of the Client’s personnel 4 |  |  |

1	Delete items that are not applicable or add other items according to Paragraph Reference 3.6 of the Data Sheet.

2	Indicate unit cost.

3	Indicate route of each flight, and if the trip is one- or two-ways.

4	Only if the training is a major component of the assignment, defined as such in the TOR.

# SECTION 5: TERMS OF REFERENCE

Background

- Urbanization presents one of the key challenges and, at the same time, opportunities in the new millennium. Urbanization is taking place at a rapid pace and is beyond the effective control of most government across the world. Even in jurisdictions where growth control boundaries have been implemented, such as Portland, such boundaries have been repeatedly revised to meet the demands for growth. The scale and complexity of urban problems are increasing everywhere. All cities must plan ahead to enable a sustainable future in the rapidly changing urban environment. Cities must review their strategic plans to develop better economic, social and environmental future. Those cities that fail to plan ahead and execute the pans will not be competitive in the globalized world. Urban economies are contributing significantly more to national exchequer and at the same time have become key employment markets. Cities indeed are important engines of economic growth and provide significant economies of scale in the provision of jobs, housing and services.

- The cities in Punjab, Pakistan are not only confronted with the task of managing unprecedented population growth, but are also under tremendous pressure to adequately cope with the resultant demands on urban land and infrastructure services.

- The Government of the Punjab intends to develop urban areas of the Province as sustainable, livable and well managed engines of economic growth. Lahore and its surrounding cities/towns have expanded greatly accommodating almost half population of the Province, and hence require a comprehensive, strategic, regional, and long-term plan.

RATIONALE FOR THE STUDY

- Since the Integrated Master Plan 2021 for Lahore was prepared in 2004, rapid urbanization of the City of Lahore and its surrounding towns has changed its economic & socio-economic characteristics and urban form. The urban area of Lahore has expanded much beyond the limits of defunct metropolitan corporations, resulting in unregulated urban sprawl and has even expanded up to the urban areas of Sheikhupura and Kasur.

- The estimated population of Lahore is around nine million, whereas the population of Lahore Division is estimated to be close to 15 million, further expected to double in next twenty five years. This implies, if the current trend of unplanned and unregulated growth has to continue, another Lahore City will be required to accommodate additional population of future, with poor quality of life and services delivery. Moreover, due to reliance on outdated estimates and secondary data, the requirements of future urban Lahore cannot be worked out.

- In addition to spatial and physical expansion and lack of reliable data & studies on the existing profile of the City and Region, the Institutional set up of services delivery and Governance in Punjab and Lahore has undergone major changes during past few years, which requires carrying out of preparation of a master plan. The previous master plans and studies kept narrow focus on land use planning and lacked strategic vision and focus on economic development, environmental conditions, financial and implementation arrangements.

- The City District Government, Lahore in collaboration with the District Governments of Kasur, Sheikhupura and Nankana Sahib, therefore have assigned the Lahore Development Authority (LDA) to hire services of a reputed international firm having vast experience in strategic, and urban and regional planning.

STUDY AREA

- The study area includes all urban areas/cities within Lahore Division which are likely to urbanize in next twenty years, to be later demarcated as the “Lahore Region”. The study will include all urbanized areas including cantonment and Defence. A map shall be provided by the client demarcating urban and non-urban areas for reference and highlighting the area of interest.

GoAL & Objectives of the study

- The overall goal of the ISDP-35 is to facilitate improved urban governance, and regional economic development in the Lahore Region to achieve economic, social, physical, environmental, and cultural sustainability, and consequently to improve the quality of life of inhabitants. This broader goal will be achieved through the following objectives and strategies.

- The main objectives of the ISDP-35 should include:

- Formulation of “vision” for the growth and development of the Lahore Region in consultation with decision makers, professionals, academia, civil society, students, and general public;

- Improved economic productivity & financial sustainability through a 3-5 years rolling financing plan, Integration of a revenue collection/generation system which incorporates efficiency, transparency and accountability; and identification of buoyant sources of municipal tax revenue etc.

- Efficient land use planning & growth management;

- Improved mobility & accessibility across region for work/education and recreation including focus on non-motorized transportation;

- Social inclusion & poverty reduction;

- Improved access to basic services & public amenities including establishment of standards for municipal service delivery;

- Improved urban environment including adaptation to the impacts of climate change and energy conservation;

- Disaster risk management;

- Infrastructure Management   maintenance, and efficient and cost effective use of existing infrastructure;

- Development of specific plans, programs and financing mechanisms for providing new infrastructure to support growth and infrastructure deficiencies;

- Standardization and beautification of streetscape through formulated urban design guidelines;

- Conservation, preservation & restoration of historical sites & built heritage for promoting tourism;

- Conservation & promotion of  local culture;

- Development of financially self-sustaining entertainment infrastructure including but not limited to parks/theme parks/amusement, playgrounds, gardens, theatres, cultural complex etc.; and

- Enabling environment and framework for private sector participation.

SCOPE OF WORK

- The Scope of this assignment is to prepare Integrated Strategic Development Plan 2035 for Lahore Region including, formulation of vision, regional economic development plan, comprehensive and regional land use plan, strategic short, medium and long term projects/actions, and implementation arrangements including institutional framework and financial plans and as well as provision of periodic revision of plan.

- The ISDP-35 has to be linked with the National Growth Strategy 2012, should be based on primary data, and must have flexibility to adapt under any potential change in the provincial legal & regulatory framework.

- While formulation of vision for the ISDP-35, the consultants have to dovetail findings, dialogue reports, and vision document prepared under the study titled “Urban Governance Framework in Lahore” being carried out by the Center for Public Policy & Governance, FC College, Lahore to avoid duplication of efforts.

- The plan shall include preparation of strategy and action plans with performance indicators and monitoring mechanisms for at least the following sub-sectors: regional land use planning, public space management, environment planning and management, water supply and wastewater management, Waste Management, urban and non-motorized transport strategy etc.

- All mapping under the ISDP-35 needs to be GIS based on freshly acquired satellite imagery. However, resolution of imagery can be different for different types of areas.

- For built up urban areas, 0.5 m resolution is recommended. For the rest of the areas (rural areas) 10 m resolution is recommended. For guidance, a map with approximate urban and rural areas shall be provided by the client. Consultant has to procure fresh imagery, and add costing in the proposal. Since the client will pay for it, it will be transferred to the client after assignment is completed including any value addition by the consultant.

- Extensive consultation with all stakeholders including but not limited to government officials, civil society, business groups, trade associations, academia, and citizens etc. will be part of the ISDP-35 study.

- In addition to extensive consultation, the Consultants will be required to engage the client’s counterpart team at all steps and shall transfer all data, information and models/databases/applications prepared for allowing them to use for other cities in future.

The client’s dedicated counterpart team will be available to the consultants for liaison; however, the consultants will have to totally depend upon their own team for all exercises.

TASKS

- Following points elaborate the scope of work:

  - Formulation of Vision:

    - The vision statement should capture the unique role of Lahore Region in the Province and the Country.

    - The vision must be rationalized against capabilities, potentials and opportunities as well as limitations and threats to ensure appropriate matching between targets and capabilities.

    - Long term collective vision for the Region with short term strategies must be aligned with a time frame and clear targets.

  - Profile of Lahore Region:

    - The profile of Lahore Region will be based on both literature review and comprehensive exercise of surveys. Primary data collection should be carried out including, but not limited to the

      - Historical maps and spatial growth patterns  in urban areas including land use classification and prevailing rules and regulations;

      - socio-economic survey @ sample size of 1% of population (Demographic composition, distribution, change, and anticipated growth patterns, employment, income level, poverty, education, health, private-formal & informal);

      - economic survey (including types of economic activities, employment trends, share of each activity in total economy and income levels etc on the sample size mentioned at b) above, Inventory and emerging pattern of businesses, commercial areas/centers, Industrial growth and trends, and projected needs etc. on areas/zones basis);

      - governance (institutions and their planning and implementation capabilities, legislation and financial resources)

      - housing survey @ sample size of 1% (Total housing units, occupancy ratio, owned versus rental housing, vacant houses, housing  backlog, housing condition, informal settlements/katchi abadies/slums, projected needs, and existing projects/programs etc. )

      - urban environment and ecology (topography, soil type, classification and suitability, land cover (vegetation, and water bodies), mineral resource information, pollution levels, water resources, climatologically conditions including average temperature, rainfall etc);

      - environmentally protected areas, risk and hazard prone areas, present disaster management framework etc;

      - Infrastructure profile documenting availability, quality and level of service (total road length, level of service, farm to markets access, pedestrian and non-motorized network, water supply, sanitation, sewerage and drainage infrastructure, health care, education, recreation, building conditions, power, communication and information technology etc.); and

      - Tourism sector profile and trends including types of tourism facilities and infrastructure, location, area occupied and ownership, quality of service, economic generation and projected needs etc.

    - The consultant will be expected to document the Region’s Profile based on the primary data (for both urban & rural areas) and interviews with the stakeholders for deeper understanding of the key issues. In this regard, both quantitative and qualitative data should be collected.

    - In addition to carrying out surveys and studies, previously prepared plans, studies, surveys, statistics, initiatives and reports should be consulted and taken into account.

    - All  collected data should be collated using GIS software

    - While carrying out transport related surveys and studies, the consultants must review work done under the JICA funded Lahore Transport Master Plan and update the surveys where required. Since the study area of Lahore Transport Master Plan was different than the ISDP-35, fresh surveys will be required in the areas not covered under that study.

  - Assessment Report

    - The consultants should carry out detailed analyses of all collected data and information after profile compilation. This should include careful examination of each sector’s profiles, growth patterns, infrastructure and facilities, existing policies supporting or constraining sectoral activities, major initiatives and programs etc.

    - The compilation should follow a series of SWOT analyses including first summarizing (sector-wise) findings and observations in SWOT framework, inter-sectoral assessment, and an aggregate/integrated SWOT analysis. This aggregate/integrated SWOT matrix will provide a composite picture of internal and external forces which will become basis for formulation of strategies.

    - In addition to detailed assessment of each sector, this report should carry out comprehensive spatial assessment seeking reasons of prevailing growth patterns and assessment of future growth requirements.

    - The assessment report should also identify strategic issues in each sector, including unique resources & comparative advantage.

    - In addition to sectoral situation analysis, the assessment report should also assess the government’s master planning and implementation capability including available financial resources and policy environment.

  - Formulation of Strategic Development Plan

The Strategic Development Plan will consist of the following sub-tasks:

    - The consultants will be required to formulate strategies to achieve the formulated vision, goals and objectives. These strategies will include but not limited to spatial planning strategy, social sector strategy, water supply, sewerage & drainage strategy, solid waste management strategy, traffic and transport strategy, environmental sustainability strategy, culture, heritage & preservation strategy, land resource management strategy, economic development strategy, financial planning  and management strategy, information management strategy, public-private-people partnership strategy, and disaster risk reduction and management strategy etc.

    - The consultants will be required to determine whether the formulated strategies are realistic, and also to identify barriers in realization of the same.

    - The consultants will be required to map existing land uses of the   study area, demarcate peri-urban boundaries around all developed urban areas and prepare  their structure plans as per the Punjab Land Use (Classification, Reclassification & Redevelopment) Rules 2009.

(While devising peri-urban boundary for the City of Lahore and preparing its structure plan, the consultants must take on board all concerned departments of the Government of the Punjab especially Environment Protection Department, Board of Revenue, Irrigation Department, Forestry, Wildlife and Fisheries Department etc. in such a way that the plan is acceptable to all concerned departments for adopting for planning purposes.)

    - The consultants will be required to identify sectoral plans/programs/projects in line with the strategies required under para d(i), and will need to break them into short, medium and long term plans/programs/projects. While identifying programs and projects, the Disaster Risk Reduction and Management (DRRM) measures must be considered.

    - The consultants will be required to provide a road map/action plan prioritizing the programs/projects required under para d(iv) including pre-feasibility (for plans/projects to be initiated within 2-3 years of preparation of ISDP-35 whether they are short-term, medium-term or long-term),  roles & responsibilities, timeframe, verifiable indicators of achievement, assumptions and risks, and indicative cost for the short term projects.

  - Implementation Framework & Guidelines:

The consultants will be required to prepare implementation framework including Institutional development/strengthening guidelines, Legal & Regulatory guidelines and Financing guidelines for the ISDP-35 including  the following:

    - A responsive institutional arrangement to enable the Local Governments within Lahore Region and LDA to effectively implement the strategies with clear demarcation of roles, rights and responsibilities of public sector, private sector, civil society, academia and general public. Suggestive improvement in performance of existing institutions through capacity enhancement may also be included in this section

    - A 3-5 years rolling financing plan and financing options including public-private partnership (including but not limited to BOT, BOOT, DBOT, joint ventures, grants, co-financing etc). It should include short, medium and long term projects for each sector, prioritization of projects in each sector, detailed costing of prioritized projects for next five years, funds availability and implementation framework, roles and responsibilities.

  - Monitoring & Evaluation Framework

A Monitoring and Evaluation Framework needs to be built into the preparation process of ISDP-35 since its inception. Therefore, the consultants will be required to develop a detailed M&E plan for ISDP-35 to detail M&E processes for at least the following stages:

    - While formulating the vision

    - While indicators are being finalized in the formats of data collection

    - While finalizing the  assessment report especially sector specific and integrated SWOT Analyses

    - While finalizing selection of plans/programs and projects

    - While plan will be implemented.

  - Communication & Consultation Plan

    - The Integrated Strategic Development Plan (ISDP-35) needs to be well communicated to all stakeholders for their ownership as well as successful implementation. The consultants are therefore required to prepare a comprehensive communication plan. The consultants are required to have extensive stakeholders consultations before and during preparations of the ISDP-35. The stakeholders include but not limited to government officials, elected representatives, professionals, practitioners, civil society members, builders & developers, academia, students and citizens of Lahore Region.

    - The consultants are required to carry out at least the following consultative sessions. The consultant have to arrange the venues for all consultation sessions and costing of workshops include rental for those.

| Name of Workshop | No. of Workshops |
| --- | --- |
| Inception Workshop | 01 |
| Consultation Workshops on: | 10 |
| - Vision Building | 01 |
| - Finalizing Indicators | 01 |
| - Finalization of Region’s Profile | 01 |
| - SWOT Analysis | 02 |
| - Finalization of Assessment Report | 02 |
| - Draft Strategic Development Plan | 02 |
| - Finalization of ISDP-35 | 01 |

    - The consultants will be required to include wide dissemination of findings and recommendations from time to time during plan preparation in their communication plan.

FIRM’S EXPERTISE

- The consulting firm must be well versed with the techniques and methodology for preparing strategic development, comprehensive and regional plans. The consulting firm must be a multi-disciplinary team of professionals and technical personnel. The firm must have the capacity to use different analytical techniques and software; and must demonstrate past experience of conducting similar studies for large cities or city regions.  The local consulting firms forming consortiums with reputable international firms will be preferred.

Deliverables

The Consultants shall submit following deliverables in digital format/soft copy and hard copies.

  - Key Deliverables

- Inception report (10  hard copies & 10 sets of CDs)

- Draft Integrated Strategic Development Plan

      - 10  hard copies of Final Report & 10 sets of CDs

      - 10 Hard copies of map of Lahore Region @ scale of 1:250,000

      - 10 Hard copies of maps of urban areas @ scale of 1:20,000

- Final Report on Integrated Strategic Development Plan 2035 for Lahore Region

      - 20  hard copies of Final Report & 20 sets of CDs

      - 20 Hard copies of map of Lahore Region @ scale of 1:250,000 in PDF format

      - 20 Hard copies of maps of urban areas @ scale of 1:20,000 in the PDF format

- (All maps and files are to be provided to the client in the ESRI compatible format. The consultants are required to provide maps of Lahore Division on the 1:250,000 scale and the maps of the districts at scale of 1:20,000. The maps will be printed in standard colours)

      - All collected processed and unprocessed data and analyses models in CDs (2 sets)

  - Miscellaneous Deliverables (10 sets of hard copies and CDs)

- Report on Vision Statement, Goals and Objectives

- Profile of Lahore Region (including all data collected and analyses in soft format)

- Assessment Report

- Strategic Sectoral Plans including but not limited to

    - Strategic Economic Development Plan

    - GIS based comprehensive Land Use Plan including Peri-Urban Structure Plan in line with the Economic Development Plan

    - Traffic & Transport Plan including non-motorized transportation

    - Water Supply, Sewerage & Drainage Plan

    - Solid Waste Management Plan

    - Public Space Management Plan

- Implementation Framework & Guidelines

    - Institutional Development Guidelines

    - Legal & Regulatory Guidelines

    - Financial Planning Guidelines

- Monitoring and Evaluation Framework

- Communication Plan & Workshops Report

- Consultation / Workshop Report

BIDDING

- Selection of consulting firm will be carried out using “One Stage - Two Envelope Bidding Procedure” as per Consultants Selection Guidelines of the Planning & Development Department, GoPb.

GENERAL CONDITIONS

- Following shall be the general conditions:

- The time period for the completion of the study shall be twenty four months from signing the contract.

- All documents shall be prepared in English and submitted on electronic media as Adobe PDF files.

- All documents produced / software prepared / GIs / IT application / analyses models / maps / images and other outputs shall be the property of the LDA and Consultant shall not use for any other purpose without the permission of the DG LDA.

- The Consultants may be required to perform any other services deemed necessary by the Client during the execution of this Contract towards the achievement of general objectives as given above.

- The consultant will be required to work in close coordination with the LDA & other Government Department/agencies.

- The Consultant will be required to hold extensive consultations and presentations with the stakeholders.

SPECIAL CONDITIONS

- All databases, maps and digital models developed under this assignment will be the property of the Government of the Punjab and the consultants will have to transfer all those assets in their original form to the ISDP-35 Working Group.

MONTH OF COMMENCEMENT AND COMPLETION

- Commencement date 	    	3rd week of August 2013

Completion period 			2-years from the date of commencement.

INDICATIVE TIME FRAME

- Indicative timeframe for services to be provided by the consultants

| Sr. No. | Scope of Services | Time |
| --- | --- | --- |
|  | Inception report | 1 Month |
|  | Report on Vision Statement, Goals and Objectives & Strategies | 2Months |
|  | Profile of Lahore Region (including all data collected and analyses in soft format) | 6 Months |
|  | Assessment report | 2Months |
|  | Draft Integrated Strategic Development Plan | 6 Months |
|  | Sectoral Plans | Overlapping 2-3 Months |
|  | Implementation Framework & Guidelines |  |
|  | Monitoring and Evaluation Framework |  |
|  | Communication Plan & Workshops Report |  |
|  | Final Report on Integrated Strategic Development Plan 2035 for Lahore Region | 04 Months |

Note :

- Total time period to complete the job for the assignment is 24 months.

- Time of approval of the documents shall not be included in the above time schedule.

- Approved TORs shall be an integral part of the contract agreement to be executed between the client and the Bidder.

PERSONNEL REQUIREMENTS

- PROFESSIONAL AND TECHNICAL

| Sr. No. | Key Staff |  |
| --- | --- | --- |
|  | Team Leader (Strategic Development Expert in Urban Strategic Development Planning) | 1 No. with at least 15 years of experience |
|  | Urban Planner | 1 No. with 15 years experience |
|  | Urban Economist | 1 No. with 12 years experience |
|  | Traffic and Transportation Expert | 1 No. with 12 years experience |
|  | Financial Analyst | 1 No. with 10 years experience |
|  | Institutional Development Specialist | 1 No. with at least 12 years of experience |
|  | Municipal Services (Water & Sanitation & Solid Waste Management) expert | 1 No. with 10 years experience |
|  | Urban Environmentalist | 1 No. with 7-10 years experience |
|  | Urban / Public Space Management Expert / Urban Designer / Landscapist / Horticulturist | 1 No. with 5-7 years experience |
|  | Support Staff |  |
|  | GIS Expert | 1 No. with 8-10 years experience |
|  | Urban Sociologist | 1 No. with 10-15 years experience |
|  | Monitoring and Evaluation Expert | 1 No. with 7-10 years experience |
|  | Communication Specialist | 1 No. with 7-10 years experience |
|  | Research Associates |  |

- Note: While evaluating the proposal, the CVs of only key staff members mentioned in the above table will be evaluated

- REPORTING REQUIREMENTS:

- ISDP-35  Working Group

- The consultants will have to work in close collaboration with the ISDP-35 Working Group formed for Integrated Strategic Development Plan ISDP-35.

- This collaboration will be required at all steps of ISDP preparation for

  - building capacities within government of preparing the plan;

  - building ownership of government departments for successful implementation; and

  - Understanding and taking into consideration the government’s point of views and emerging needs.

- ISDP-35 Steering Committee

- All interim reports and final master plan will have to be cleared from the ISDP-35 Steering Committee before it can be submitted for Council’s approval.

- Stakeholder’s Partnership Group

- For taking stakeholders from all segments of society on board, a Stakeholder Partnership Group will be formed by the ISDP-35 Working Group

- However, the consultations required for this plan will not be limited to this Stakeholder Partnership Group.

|  | LAHORE DEVELOPMENT AUTHORITY LDA |  |
| --- | --- | --- |

### APPENDIX 1A

### FORMAT FOR POWER OF ATTORNEY FOR SIGNING PROPOSAL

(On a Stamp Paper of appropriate value)

# POWER OF ATTORNEY

Know all men by these presents, we ____________ (name and address of the registered office) do hereby constitute, appoint and authorize Mr./Ms. _____________________ (name and address of residence) who is presently employed with us and holding the position of __________________ as our attorney, to do in our name and on our behalf, all such acts, deeds and things necessary in connection with or incidental to our Proposal for the [insert name of project in the Pakistan, including signing and submission of all documents and providing information/ responses to Lahore Development Authority (LDA), representing us in all matters before GoPb, and generally dealing with LDA in all matters in connection with our proposal for the said project.

We hereby agree to ratify all such acts, deeds and things lawfully done by our said attorney pursuant to this Power of Attorney and that all such acts, deeds and things awfully done by our aforesaid attorney shall and shall always be deemed to have been done by us.

For ------------------------

(Signature)

(Name, Title and Address)

Accepted

________________ (Signature)

(Name, Title and Address of the Attorney)

Bidder seal & stamp

Notes:

1. To be executed by the sole Bidder or the Lead Member in case of a Consortium duly supported .by a Board Resolution

2. The mode of execution of the Power of Attorney should be in accordance with the procedure, if any, laid down by the applicable law and the charter documents of the executants (s) and when it is so required the same should be under common seal affixed in accordance with the required procedure.

3. Also, where required, the executants(s) should submit for verification the extract of the charter documents and documents such as a resolution / power of attorney in favor of the Person executing this Power of Attorney for the delegation of power hereunder on behalf of the Bidder.

### APPENDIX 1B

### FORMAT FOR POWER OF ATTORNEY FOR LEAD MEMBER OF CONSORTIUM

(On a Stamp Paper of appropriate value)

# POWER OF ATTORNEY

Whereas, the Lahore Development Authority (LDA) invites proposals from  interested Bidders for the [insert name of project}.

Whereas, the members of the Consortium are interested in competing for the Project in accordance with the terms and conditions of the RFP and other connected documents in respect of the Project, and

Whereas, it is necessary under the RFP for the members of the Consortium to nominate one of them as the Lead Member with all necessary power and authority to do for and on behalf of the Consortium, all such acts, deeds and things as may be necessary in connection with or incidental to the Consortium’s proposal for the Project.

# NOW THIS POWER OF ATTORNEY WITNESSETH THAT:

We, M/s. _________________, and M/s. ________________ (the respective names and addresses of the registered office) do hereby constitute, appoint and authorize M/s. __________________________ as the Lead Member of the Consortium and as our attorney, to do on behalf of the Consortium, all or any of such acts, deeds or things as may be necessary in connection with or incidental to the Consortium’s proposal for the Project, including submission of proposal, participating in conferences, responding to queries, submission of information/ documents and generally to represent the Consortium in all its dealings with Lahore Development Authority (LDA) or any other Government Agency or any person, in connection with the Project until culmination of the process of selection and thereafter till the Contract Agreement is entered into with the Lahore Development Authority (LDA).

We hereby agree to ratify all such acts, deeds and things lawfully done by Lead Member as our said attorney pursuant to this Power of Attorney and that all acts deeds and things lawfully done by our aforesaid attorney shall and shall always be deemed to have been done by us/Consortium.

Dated this _______ Day of ________ 2012_.

(Executants)

(To be executed by all the members of the Consortium)

Bidder seal & stamp

Note:

1. The mode of execution of the Power of Attorney should be in accordance with the procedure, if any, laid down by the applicable law and the charter documents of the executants(s) and when it is so required the same should be under common seal affixed in accordance with the required procedure.

2. The executants(s) should submit for verification the extract of the charter documents and documents such as Board Resolution and Power of Attorney in favor of the person executing this Power of Attorney in favor of the Lead Member.

### APPENDIX 2

## DETAILS OF BIDDER

- (a) Name

(b) Country of Incorporation

(c) Address of the corporate headquarters and its branch office (s), Pakistan

(d) Date of incorporation and / or commencement of business

- Brief description of the Bidder’s company including details of its main lines of business and proposed roles and responsibilities in this Project.

- Name, Designation, Address and Phone Nos. of Authorized Signatory of the Bidder:

(a) Name:

(b) Designation:

(c) Bidder’s Company:

(d) Address:

(e) Telephone No:

(f) E-mail Address:

(g) Fax No:

- Details of individual (s) who will serve as the point of contact / communication for the Lahore Development Authority (LDA), within the Bidder’s company.

(a) Name:

(b) Designation:

(c) Address:

(d) Telephone No.

(e) E-mail address:

(f) Fax No.

- In case of Consortium:

(a) The information above (1-4) should be provided for all the Members of the Consortium

(b) Information regarding role of each Member should be provided as per table below:

| Sr. No. | Name of Member | Lead Member / Associate | Role of the Member |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |

Specify whether Lead Member, Associate Member

(Signature of Authorized Signatory)

Bidder seal & stamp

### APPENDIX 3

### FORMAT FOR LETTER OF PROPOSAL APPLICATION

[On the Letter Head of the Bidder  (in case of Single or Lead Member (in case of a Consortium)]

Date: ------------

The Chief Metropolitan Planner,

Lahore Development Authority (LDA)

[insert name of Project]

Sir,

Being duly authorized to represent and act on behalf of _________________ (hereinafter referred to as "the Bidder"), and having reviewed and fully understood all of the qualification requirements and information provided, the undersigned hereby expresses its interest and apply for qualification for the [insert name of Project].

We are enclosing our Proposal, in one Original and two Copies, with the details as per the requirements of the RFP, for your evaluation.

The undersigned hereby also declares that the statements made and the information provided in the RFP are complete, true and correct in every detail.

We confirm that the Proposal application is valid for a period of 90 days from the due date of submission of Proposal application and is unconditional.

Yours faithfully,

(Signature of Authorized Signatory)

(Name, Title and Address of the Bidder)

Bidder seal & stamp

### APPENDIX 4

### LETTER OF INTENT TO FORM A CONSORTIUM

[On the Letter Head of the Bidder (in case of Single Entity) or Lead Member (in case of a Consortium)]

Date: ------------

The Chief Metropolitan Planner,

Lahore Development Authority (LDA)

[insert name of Project]

Sir,

We, ………………………………………… hereby convey our intent to form a consortium with ………………………………………… and ……………………………………. for the successful execution of the captioned Project. The Lead member of the Consortium will be ……………………………………... .

We commit to provide the following appendices and documents before the RFP submission deadline:

1. Appendix 1A – The Power of Attorney for signing authority

2. Appendix 1B – The Power of Authority for Lead Member

3. Appendix 10 - Duly notarized MOU of the Consortium.

4. Documentary Evidence

The mode of execution of the Power of Attorney would be in accordance with the procedure, if any, laid down by the applicable law and the charter documents of the consortium members and when it is so required the same would be under common seal affixed in accordance with the required procedure.

The consortium members would submit for verification the extract of the charter documents and documents such as Board Resolution and Power of Attorney in favor of the person executing this Power of Attorney in favor of the Lead Member.

Yours faithfully,

(Signature of Authorized Signatory)

(Name, Title and Address of the Bidder)

Bidder seal & stamp

### APPENDIX 5

### FORMAT FOR ANTI-COLLUSION CERTIFICATE

[To be submitted on the letter heads of the Bidder separately]

Anti-Collusion Certificate

Date: ------------

The Chief Metropolitan Planner,

Lahore Development Authority (LDA)

[insert name of Project]

Sir,

We hereby certify and confirm that in the preparation and submission of this Proposal, we have not acted in concert or in collusion with any other Bidders or other person(s) and also not done any act, deed or thing which is or could be regarded as anti-competitive, restrictive or monopolistic trade practice.

We further confirm that we have not offered nor will offer any illegal gratification in cash or kind to any person or agency in connection with the instant Proposal.

Dated this ______________ Day of ________________, 2013_

Name of the Bidder

Signature of the Authorized Person

Note:

To be submitted by each Member in case of Consortium.

### APPENDIX 6A

### FORMAT FOR PROJECT UNDERTAKING

[In case of Single Bidder]

[To be submitted on the letter heads of the Bidder separately]

Date: ------------

The Chief Metropolitan Planner,

Lahore Development Authority (LDA)

[insert name of Project]

Sir,

We have read and understood the RFP Document in respect of the captioned Project provided to us from the CMP Counter, One Window Cell, Lahore Development Authority 467-DII Johar Town Lahore, Pakistan

We hereby agree and undertake as under:

(a)	Not withstanding any qualification or conditions, whether implied or otherwise, contained in our Proposal, we hereby represent and confirm that our Proposal is unqualified and unconditional in all respects.

(b)	We are not barred by the Government or any of its Department or Agency from participating in any project.

Dated this ___________________ Day of _______________, .

Name of the Bidder

_________________________________

Signature of the Authorized Person

Bidder seal & stamp

### APPENDIX 6B

### FORMAT FOR PROJECT UNDERTAKING

[In case of Consortium]

[To be submitted on the letter heads of the Bidder separately]

Date: ------------

The Chief Metropolitan Planner,

Lahore Development Authority (LDA)

[Insert name of Project]

Sir,

We have read and understood the RFP Document in respect of the captioned Project provided to us from the CMP Counter, One Window Cell, Lahore Development Authority 467-DII Johar Town Lahore, Pakistan

We hereby agree and undertake as under:

We hereby agree and undertake to be an exclusive member of the consortium and not a member of any other consortium nor an independent bidder, applying for this Project and have submitted only one (1) Proposal Application in response to this RFP

Dated this ___________________ Day of _______________, .

Name of the Bidder

_________________________________

Signature of the Authorized Person

Bidder seal & stamp

### APPENDIX 7

### FORMAT FOR MEMORANDUM OF UNDERSTANDING (MOU)

(On Non – judicial stamp paper of appropriate value duly attested by notary public)

This Memorandum of Understanding (MOU) entered into this _____day of _______ 2013 at ______ Between _______________(hereinafter referred as”________”) and having office at _______, Pakistan. Partyof the First Part

And

________(hereinafter referred as”__________”) and having office at ____________, Pakistan

Party of the Second Part. The member is individually referred to as Party and collectively as Parties.

WHEREAS the Lahore Development Authority (LDA) has invited Request for Proposal (RFP) from short listed bidders in [insert name of Project].

AND WHEREAS the Parties have had discussions for formation of a Consortium for competing for the said project and have reached an understanding on the following points with respect to the Parties’ rights and obligations towards each other and their working relationship.

IT IS HEREBY AS MUTUAL UNDERSTANDING OF THE PARTIES AGREED AND DECLARED AS FOLLOWS:

1. 	The parties undertake that there shall be no changes in respect of the lead member in case of a consortium till the execution of the contract agreement.

2. 	That the Parties shall carry out all responsibilities which will be specified in terms of the Contract Agreement.

3. 	That the roles and the responsibilities of each Party at each stage of the section shall be as follows:

| Name of the Member | Type of Member | Roles and Responsibilities |
| --- | --- | --- |

4. 	That the Parties shall be jointly and severally liable for the execution of the Project in accordance with the terms of the Contract agreement to be executed on award of the Project.

5. 	That the Parties affirm that they shall execute the Project in good faith and shall take all necessary steps to see the Project through expeditiously. They shall not negotiate with any other party for this Project.

6. 	That this MOU shall be governed in accordance with the laws of Pakistan and courts in Punjab shall have exclusive jurisdiction to adjudicate disputes arising from the terms herein.

In witness whereof the Parties affirm that the information provided is accurate and true and have caused this MOU to be duly executed on the date and year above mentioned.

Witness:

1. First Party

2. Second Party

Bidder seal & stamp

### CHECKLIST OF DOCUMENTS TO BE SUBMITTED

- Proposal containing the following:

- Original

- 2 Copies

- Contents of RFP:

- Power of Attorney for signing of proposal (Appendix 1A)

- Power of Attorney for lead member of consortium (Appendix 1B)

- Details of Bidders (Appendix 2)

- Letter of Invitation (Appendix 3)

- Letter of intent to form a Consortium (Appendix 4)

# Format for anti-collusion certificate (appendix 5)

# Format for project undertaking (appendix 6a & 6b)

# Format for memorandum of understanding (MOU) (appendix 7)

Standard Form of Agreement– Lump-Sum Payments

(LARGE)

INSTRUCTIONS TO USERS

- Lump-sum contracts are normally used when definition of the tasks to be performed is clear and unambiguous, when the commercial risk taken by the Consultant are relatively low, and when therefore such Consultant are prepared to perform the assignment for an agreed predetermined lump-sum price. Such price is arrived at on the basis of inputs - including rates - provided by the Consultant. The Client agrees to pay the Consultant according to a schedule of payments linked to the delivery of certain outputs, for example reports. A major advantage of the lump-sum agreement is the simplicity of its administration, the Client having only to be satisfied with the outputs without monitoring the staff inputs. Studies are usually carried out on a lump-sum basis: for example, surveys, master plans, economic, sector, simple feasibility and engineering studies.

- The Agreement includes four parts: the Form of Agreement, the General Conditions of Agreement, the Special Conditions of Agreement, and the Appendices. The Client using this standard agreement should not alter the General Conditions. Any adjustment to meet specific project features should be made only in the Special Conditions.

- Instructions to users are also provided in various places of this document within parenthesis or as Note(s). Users are expected to edit and finalise this document accordingly, by filling all the blank spaces and forms, deleting all the notes and instructions intended to help the users.

AGREEMENT FOR CONSULTANCY SERVICES

LUMP SUM

between

_________________________________________________

(NAME OF THE CLIENT)

and

____________________________________________________

(NAME OF THE CONSULTANTS)

for

_________________________ (BRIEF SCOPE OF SERVICES)

OF __________________________________ (NAME OF PROJECT)

_______________________

Month and Year

FORM OF AGREEMENT

[Notes:

- Use this Form of Agreement when the Consultants perform Services as Sole Consultants.

- In case the Consultants perform Services as a Member of the joint venture, use the Form included at the end.

- All notes should be deleted in the final text.]

This AGREEMENT (hereinafter called the "Agreement") is made on the __ day of __ month) of ___ (year), between, on the one hand ______________________________

(hereinafter called the "Client" which expression shall include the successors, legal representatives and permitted assigns) and, on the other hand, __________________________________________________________________ (hereinafter called the "Consultants" which expression shall include the successors, legal representatives and permitted assigns).

WHEREAS

(a)	the Client has requested the Consultants to provide certain consulting services as defined in the General Conditions of Agreement attached to this Agreement (hereinafter called the "Services"); and

(b)	the Consultants, having represented to the Client that they have the required professional skills, and personnel and technical resources, have agreed to provide the Services on the terms and conditions set forth in this Agreement;

NOW THEREFORE the Parties hereby agree as follows:

1.	The following documents attached hereto shall be deemed to form an integral part of this Agreement:

(a)	the General Conditions of Agreement;

(b)	the Special Conditions of Agreement;

(c)	the following Appendices:

[Note: If any of these Appendices are not used, the words "Not Used" should be inserted below/next to the title of the Appendix and on the sheet attached hereto carrying the title of that Appendix.]

Appendix A : Description of the Services

Appendix B : Reporting Requirements

Appendix C : Key Personnel and Subconsultant

Appendix D : Breakdown of Agreement Price

Appendix E : Services & Facilities to be Provided by the Client

Appendix F : Form of Advance Payments Guarantee

2.	The mutual rights and obligations of the Client and the Consultants shall be as set forth in the Agreement, in particular:

(a)	the Consultants shall carry out the Services in accordance with the provisions of the Agreement; and

(b)	the Client shall make payments to the Consultants in accordance with the provisions of the Agreement.

IN WITNESS WHEREOF, the Parties hereto have caused this Agreement to be signed in their respective names in two identical counterparts, each of which shall be deemed as the original, as of the day, month and year first above written.

For and on behalf of

_________________________

(CLIENT)

Witness

Signatures___________________	Signatures ________________

Name ______________________	Name ____________________

Title ________________________	Title _____________________

(Seal)

For and on behalf of

_________________________

(CONSULTANTS)

Witness

Signatures___________________	Signatures ________________

Name ______________________	Name ____________________

Title _______________________	Title _____________________

(Seal)

1	GENERAL PROVISIONS	83

1.1Definitions	83

1.2Law Governing the Agreement	84

1.3Language	84

1.4Notices	84

1.5Location	84

1.6Authorised Representatives	84

1.7Taxes	84

1.8AUTHORITY OF Leader of Joint Venture	85

1.9Fraud and Corruption	85

1.9.1Definitions	85

1.9.2Measures to be Taken	85

1.9.3Commissions and Fees	85

2	COMMENCEMENT, COMPLETION, MODIFICATION, AND TERMINATION OF AGREEMENT	86

2.1Effectiveness of Agreement	86

2.2Termination of Agreement for Failure to Become Effective	86

2.3Commencement of Services	86

2.4Expiration of Agreement	86

2.5Modification	86

2.6Force Majeure	86

2.6.1Definition	86

2.6..2No Breach of Agreement	87

2.6.3Measures to be Taken	87

2.6.4Extension of Time	87

2.6.5Payments	88

2.6.6Consultation	88

2.7           Termination	88

2.7.1By the Client	88

2.7.2By the Consultant	89

2.7.3Payment upon Termination	89

2.7.4Disputes about Events of Termination	89

3	OBLIGATIONS OF THE CONSULTANT	90

3.1General	90

3.2Conflict of Interests	90

3.2.1Consultant Not to Benefit from Commissions, Discounts, etc	90

3.2.2Consultant and Affiliates not to be otherwise interested in Project	90

3.2.3Prohibition of Conflicting Activities	90

3.3Confidentiality	91

3.4Liability of the Consultant	91

3.5Other Insurances to be Taken out by the Consultant	91

3.6Consultant’s Actions Requiring Client's Prior Approval	91

3.7Reporting Obligations	92

3.8Documents Prepared by the Consultant to be the Property of the Client	92

3.9Equipment, Vehicles and Materials Furnished by the Client	92

4	CONSULTANT'S PERSONNEL AND SUBCONSULTANT	92

4.1General	92

4.2Removal and/or Replacement of Personnel	93

5	OBLIGATIONS OF THE CLIENT	93

5.1Assistance, Coordination and Approvals	93

5.2Access to Land	93

5.3Change in the Applicable Law	94

5.4Payments	94

6	PAYMENTS TO THE CONSULTANT	94

6.1Lump Sum Remuneration	94

6.2Agreement Price	94

6.3Terms and Conditions of Payment	94

6.4Period of Payment	94

6.5Delayed Payments	95

7	FAIRNESS AND GOOD FAITH	95

7.1Good Faith	95

8	SETTLEMENT OF DISPUTES	95

8.1Amicable Settlement	95

8.2Dispute Settlement	95

# GENERAL CONDITIONS OF AGREEMENT

# 1	GENERAL PROVISIONS

## Definitions

Unless the context otherwise requires, the following terms whenever used in this Agreement have the following meanings:

- "Agreement" means the Agreement signed by the Parties, to which these General Conditions of Agreement (GC) are attached, together with all the documents listed in Clause  of such signed Agreement;

- "Applicable Law" means the laws and any other instruments having the force of law in the Islamic Republic of Pakistan, as those may be issued and in force from time to time;

- "Assignment" means the work specified in SC for which consultancy services are desired.

- “Consultant” means the Party that will provide the Services to the Client under the Agreement

- "Effective Date" means the date on which this Agreement comes into force and effect pursuant to Clause ;

- "GC" means these General Conditions of Agreement;

- "Government" means the Government of the Islamic Republic of Pakistan;

- "Foreign Currency" means currency other than the currency of Islamic Republic of Pakistan;

- "Local Currency" means the currency of the Islamic Republic of Pakistan;

- "Member" in case the Consultant consist of a joint venture of more than one entity, means any of the entities, and "Members" means all of these entities;

- "Party" means the Client or the Consultant, as the case may be, and "Parties" means both of them;

- "Personnel" means persons hired by the Consultant or by any Subconsultant as employees and assigned to the performance of the Services or any part thereof;

- “Reimbursable expenditures” means assignment related costs other than Consultant’s remuneration.

- "SC" means the Special Conditions of Agreement by which the GC are amended or supplemented;

- "Services" means the work to be performed by the Consultant pursuant to this Agreement, as described in Appendix A;

- "Subconsultant" means any entity to which the Consultant subcontracts any part of the Services in accordance with the provisions of Clause ;

- "Third Party" means any person or entity other than the Client, the Consultant or a Subconsultant.

## Law Governing the Agreement

This Agreement, its meaning and interpretation, and the relation between the Parties shall be governed by the Applicable Law.

## Language

This Agreement has been executed in the English language which shall be the binding and controlling language for all matters relating to the meaning or interpretation of this Agreement. All reports and communications pertaining to the Agreement shall be in the English language.

## Notices

Any notice, request, or consent required or permitted to be given or made pursuant to this Agreement shall be in writing and shall be deemed to have been given or made when delivered in person to an Authorised Representative of the Party to whom the communication is addressed, or when sent by registered mail, telex, or facsimile to such Party at the address of the Authorised Representative specified under Clause SC . A Party may change its address for notice hereunder by giving the other Party notice of such change in writing.

## Location

The Services shall be performed at such locations as are specified in Appendix A and, where the location of a particular task is not so specified, at such locations as the Client may approve.

## Authorised Representatives

Any action required or permitted to be taken, and any document required or permitted to be executed, under this Agreement by the Client or the Consultant shall be taken or executed by the Authorised Representatives specified in the SC.

## Taxes

Unless specified in the SC, the Consultant, Subconsultant, and their Personnel shall pay such taxes, duties, fees, and other impositions as may be levied under the Applicable Law, the amount of which is deemed to have been included in the Agreement price.

## Authority of Leader of Joint Venture

In case the Consultant consists of a joint venture of more than one entity, the Members hereby designate the Member specified in SC as Leader of the Joint Venture to act on their behalf in exercising all the Consultant’s rights and obligations towards the Client under the Agreement, including without limitation, the receiving of instructions and payments from the Client.

## Fraud and Corruption

Both parties to the Agreement must observe the highest standard of ethics during the execution of the Agreement.

### Definitions

In pursuance of this policy, the following terms are defined:

- “corrupt practice” means the offering, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of a public official in the selection process or in agreement execution;

- “fraudulent practice” means a misrepresentation or omission of facts in order to influence a selection process or the execution of a agreement;

- “collusive practices” means a scheme or arrangement between two or more Consultant, with or without the knowledge of the Borrower, designed to establish prices at artificial, noncompetitive levels;

- “coercive practices” means harming or threatening to harm, directly or indirectly, persons or their property to influence their participation in a procurement process, or affect the execution of a agreement;

### Measures to be Taken

In pursuance of this policy, the Client:

- will sanction a Consultant, including declaring the Consultant ineligible, either indefinitely or for a stated period of time, to be awarded a Agreement if it at any time determines that the Consultant has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for, or in executing, an Agreement;

### Commissions and Fees

In pursuance of this policy, the successful Consultant will be required to disclose any commissions or fees that may have been paid or are to be paid to agents, representatives, or commission agents with respect to the selection process or execution of the agreement. The information disclosed must include at least the name and address of the agent, representative, or commission agent, the amount and currency, and the purpose of the commission or fee.

# COMMENCEMENT, COMPLETION, MODIFICATION, AND TERMINATION OF AGREEMENT

## Effectiveness of Agreement

This Agreement shall come into force and effect on the date (the "Effective Date") of the Client's notice to the Consultant instructing the Consultant to begin carrying out the Services. This notice shall confirm that the effectiveness conditions, if any, listed in the SC have been met.

## Termination of Agreement for Failure to Become Effective

If this Agreement has not become effective within such time period after the date of the Agreement signed by the Parties as shall be specified in the SC, either Party may, by not less than twenty eight (28) days written notice to the other Party, declare this Agreement to be null and void, and in the event of such a declaration by either Party, neither Party shall have any claim against the other Party.

## Commencement of Services

The Consultant shall begin carrying out the Services at the end of such time period after the Effective Date as shall be specified in the SC.

## Expiration of Agreement

Unless terminated earlier pursuant to Clause  hereof, this Agreement shall expire at the end of such time period after the effective date as specified in the SC.

## Modification

Any modification of the terms and conditions of this Agreement, including any modification of the scope of the Services, may only be made in writing, which shall be mutually agreed upon and signed by both the Parties.

## Force Majeure

### Definition

- For the purposes of this Agreement, "Force Majeure" means an event which is beyond the reasonable control of a Party, is not foreseeable, is unavoidable, and which makes a Party's performance of its obligations under the Agreement impossible or so impractical as to be considered impossible under the circumstances, and includes, but is not limited to, war, riots, civil disorder, earthquake, fire, explosion, storm, flood or other adverse weather conditions, strikes, lockouts or other industrial actions (except where such strikes, lockouts or other industrial actions are within the power of the Party invoking Force Majeure to prevent), confiscation or any other action by government agencies.

- Force Majeure shall not include (i) any event which is caused by the negligence or intentional action of a Party or such Party's Subconsultant or agents or employees, nor (ii) any event which a diligent Party could reasonably have been expected to both (A) take into account at the time of the conclusion of this Agreement and (B) avoid or overcome in the carrying out of its obligations hereunder.

- Force Majeure shall not include insufficiency of funds or failure to make any payment required hereunder.

### No Breach of Agreement

The failure of a Party to fulfil any of its obligations under the Agreement shall not be considered to be a breach of, or default under this Agreement insofar as such inability arises from an event of Force Majeure, provided that the Party affected by such an event has taken all reasonable precautions, due care and reasonable alternative measures in order to carry out the terms and conditions of this Agreement.

### Measures to be Taken

- A Party affected by an event of Force Majeure shall continue to perform its obligations under the Agreement as far as is reasonably practical, and shall take all reasonable measures to minimize the consequences of any event of Force Majeure.

- A Party affected by an event of Force Majeure shall notify the other Party of such event as soon as possible, and in any case not later than fourteen (14) days following the occurrence of such event, providing evidence of the nature and cause of such event, and shall similarly give written notice of the restoration of normal conditions as soon as possible.

- In the case of disagreement between the Parties as to the existence or extent of Force Majeure, the matter shall be settled according to Clause .

### Extension of Time

Any period within which a Party shall, pursuant to this Agreement, complete any action or task, shall be extended for a period equal to the time during which such Party was unable to perform such action as a result of Force Majeure.

### Payments

- During the period of their inability to perform the Services as a result of an event of Force Majeure, the Consultant shall be entitled to continue to be paid under the terms of this Contract, as well as to be reimbursed for additional costs reasonably and necessarily incurred by them during such period for the purposes of the Services and in reactivating the Service after the end of such period.

### Consultation

Not later than 30 days after the Consultant, as a result of an event of Force Majeure, has become unable to perform a material portion of the services, the Parties shall consult with each other with a view to agreeing on appropriate measures to be taken in the circumstances.

## Termination

### By the Client

The Client may terminate this Agreement, by not less than thirty (30) days written notice of termination to the Consultant, to be given after the occurrence of any of the events specified in paragraphs (a) through (f) of this Clause  and sixty (60) days in the case of the event referred to in paragraph (g):

- if the Consultant does not remedy a failure in the performance of its obligations under the Agreement, within thirty (30) days after being notified pursuant to 2.7, or within any further period as the Client may have subsequently approved in writing;

- if the Consultant becomes (or, if the Consultant consist of more than one entity, if any of its Members become) insolvent or bankrupt or enters into any agreement with its creditors for relief of debt or takes advantage of any law for the benefit of debtors or goes into liquidation or receivership whether compulsory or voluntary;

- if the Consultant fails to comply with any final decision reached as a result of arbitration proceedings pursuant to Clause 8 hereof;

- if the Consultant, in the judgment of the Client, has engaged in corrupt or fraudulent practices in competing for or in executing this agreement;

- if the Consultant submits to the Client a statement which has a material effect on the rights, obligations or interests of the Client and which the Consultant knows to be false;

- if, as the result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than sixty (60) days;

- if the Client, in its sole discretion, decides to terminate this Agreement.

### By the Consultant

The Consultant may terminate this Agreement, by not less than thirty (30) days written notice to the Client, such notice to be given after the occurrence of any of the events specified in paragraphs (a) through (d) of this Clause :

- if the Client fails to pay any monies due to the Consultant pursuant to this Agreement and not subject to dispute pursuant to Clause  within forty-five (45) days after receiving written notice from the Consultant that such payment is overdue;

- if the Client is in material breach of its obligations pursuant to this Agreement and has not remedied the same within forty-five (45) days (or such longer period as the Consultant may have subsequently approved in writing) following the receipt by the Client of the Consultant’s notice specifying such breach;

- if, as a result of Force Majeure, the Consultant is unable to perform a material portion of the Services for a period of not less than sixty (60) days;

- if the Client fails to comply with any final decision reached as a result of arbitration proceedings pursuant to Clause  hereof.

### Payment upon Termination

Upon termination of this Agreement pursuant to Clauses  or , the Client shall make the following payments to the Consultant:

- remuneration and reimbursable direct costs expenditure pursuant to Clause  for Services satisfactorily performed prior to the effective date of termination. Effective date of termination for purposes of this Clause means the date when the prescribed notice period would expire;

- except in the case of termination pursuant to paragraphs (a) through (d) of Clause , reimbursement of any reasonable cost incidental to the prompt and orderly termination of the Agreement.

### Disputes about Events of Termination

If either Party disputes whether an event specified in paragraphs (a) through (f) of Clause  or in paragraphs (a) through (d) of Clause  hereof has occurred, such Party may, within forty-five (45) days after receipt of notice of termination from the other Party, refer the matter to Clause  hereof, and this Agreement shall not be terminated on account of such event except in accordance with the resolution of the dispute under Clause .

# OBLIGATIONS OF THE CONSULTANT

## General

The Consultant shall perform the Services and carry out its obligations with all due diligence, efficiency, and economy, in accordance with generally accepted professional techniques and practices, and shall observe sound management practices, and employ appropriate advanced technology and safe and effective equipment, machinery, materials and methods. The Consultant shall always act, in respect of any matter relating to this Agreement or to the Services, as faithful adviser to the Client, and shall at all times support and safeguard the Client's legitimate interests in any dealings with Subconsultant or third parties.

## Conflict of Interests

The Consultant shall hold the Client’s interests paramount, without any consideration for future work, and strictly avoid conflict with other assignments or its own corporate interests.

### Consultant Not to Benefit from Commissions, Discounts, etc

The remuneration of the Consultant pursuant to Clause  shall constitute the Consultant’s sole remuneration in connection with this Agreement or the Services, and the Consultant shall not accept for its own benefit any trade commission, discount, or similar payment in connection with activities pursuant to this Agreement or to the Services or in the discharge of its obligations under the Agreement, and the Consultant shall use its best efforts to ensure that the Personnel, any Subconsultant, and agents of either of them similarly shall not receive any such additional remuneration.

### Consultant and Affiliates not to be otherwise interested in Project

The Consultant agrees that, during the term of this Agreement and after its termination, the Consultant and any entity affiliated with the Consultant, as well as any Subconsultant and any entity affiliated with such Subconsultant, shall be disqualified from providing goods, works or services (other than consulting services) resulting from or directly related to the Consultant’s Services for the preparation or implementation of the project.

### Prohibition of Conflicting Activities

The Consultant shall not engage, and shall cause their Personnel as well as their Subconsultant and their Personnel not to engage, either directly or indirectly, in any business or professional activities that would conflict with the activities assigned to them under this Agreement.

## Confidentiality

The Consultant, its Subconsultant, and the Personnel of either of them shall not, either during the term or after the expiration of this Agreement, disclose any proprietary or confidential information relating to the Project, the Services, this Agreement, or the Client's business or operations without the prior written consent of the Client.

## Liability of the Consultant

- The Consultant shall only be liable to pay compensation to the Client if it failed to exercise reasonable skill, care and diligence in the performance of its obligations under the Agreement. The limit of this liability shall be governed by SC.

- The Consultant shall not be considered liable for any loss or damage unless a claim is formally made on it before the expiry of the relevant period stated in the SC.

- The Client can request in writing that the Consultant insure against its liability under Clause (a), in which case the extent of such insurance shall be up to the limit specified in Clause (a). In case of such a request, the Consultant shall make all reasonable efforts to effect such insurance, but the cost of such insurance shall be borne by the Client.

- The Consultant shall, at the request of the Client, indemnify the Client against any or all risks arising out of the furnishing of professional services by the Consultant to the Client, not covered by the provisions of Clause (a), provided the actual cost of procuring such indemnity as well as costs exceeding the limits for maximum liability set in Clause (a) shall be borne by the Client.

## Other Insurances to be Taken out by the Consultant

The Consultant (a) shall take out and maintain, and shall cause any Sub-Consultant to take out and maintain, at its (or the Sub-Consultants’, as the case may be) own cost but on terms and conditions approved by the Client, insurance against the risks, and for the coverage, as shall be specified in the SC; and (b) at the Client’s request, shall provide evidence to the Client showing that such insurance has been taken out and maintained and that the current premiums have been paid.

## Consultant’s Actions Requiring Client's Prior Approval

The Consultant shall obtain the Client's prior approval in writing before taking any of the following actions:

- Any change or addition to the Personnel listed in Appendix-C;

- entering into a sub-agreement for the performance of any part of the Services, it being understood (i) that the selection of Subconsultant and the terms and conditions of the sub-agreement shall have been approved in writing by the Client prior to the execution of the sub-agreement, and (ii) that the Consultant shall remain fully liable for the performance of the Services by the Subconsultant and its Personnel pursuant to this Agreement;

- any other action that may be specified in the SC.

## Reporting Obligations

The Consultant shall submit to the Client the reports and documents specified in Appendix B in the form, in the numbers, and within the periods set forth in the said Appendix. Final reports shall be delivered in CD ROM in addition to the hard copies specified in said Appendix.

## Documents Prepared by the Consultant to be the Property of the Client

All plans, drawings, specifications, reports, and other documents and software prepared by the Consultant in accordance with Clause  shall become and remain the property of the Client, and the Consultant shall, not later than upon termination or expiration of this Agreement, deliver (if not already delivered) all such documents and software to the Client, together with a detailed inventory thereof.

The Consultant may retain a copy of such documents and software, and use such software for its own use with prior written approval of the Client.

Restriction(s) about the future use of these documents is specified in the SC.

## Equipment, Vehicles and Materials Furnished by the Client

Equipment, vehicles and materials made available to the Consultant by the Client, or purchased by the Consultant with funds wholly or partly provided by the Client, shall be the property of the Client and shall be marked accordingly. Upon termination or expiration of this Agreement, the Consultant shall make available to the Client an inventory of such equipment and materials and shall dispose of such equipment, vehicles and materials in accordance with the Client's instructions or afford salvage value of the same. While in possession of such equipment, vehicles and materials, the Consultant, unless otherwise instructed by the Client in writing, shall insure them at the expense of the Client in an amount equal to their full replacement value.

# CONSULTANT'S PERSONNEL AND SUBCONSULTANT

## General

The Consultant shall employ and provide such qualified and experienced Personnel and Subconsultant as are required to carry out the Services. The titles, agreed job descriptions, minimum qualifications, and estimated periods of engagement in the carrying out of the Services of the Consultant’s Key Personnel are described in Appendix C. The Key Personnel and Subconsultant listed by title as well as by name in Appendix C are hereby approved by the Client.

## Removal and/or Replacement of Personnel

- Except as the Client may otherwise agree, no changes shall be made in the Key Personnel. If, for any reason beyond the reasonable control of the Consultant, it becomes necessary to replace any of the Key Personnel, the Consultant shall provide as a replacement a person of equivalent or better qualifications.

- If the Client: (i) finds that any of the Personnel have committed serious misconduct or have been charged with having committed a criminal action; or (ii) have reasonable cause to be dissatisfied with the performance of any of the Personnel, then the Consultant shall, at the Client's written request specifying the grounds therefore, provide as a replacement a person with qualifications and experience acceptable to the Client.

- Except as the Client may otherwise agree, (i) the Consultant shall bear all additional travel and other costs arising out of or incidental to any removal and/or replacement, and (ii) bear any additional remuneration, to be paid for any of the Personnel provided as a replacement to that of the Personnel being replaced.

# OBLIGATIONS OF THE CLIENT

## Assistance, Coordination and Approvals

The Client shall use its best efforts to:

- provide at no cost to the Consultant, Subconsultant and Personnel such documents prepared by the Client or other consulting engineers appointed by the Client as shall be necessary to enable the Consultant, Subconsultant or Personnel to perform the Services. The documents and the time within which such documents shall be made available, are as specified in the SC;

- issue to officials, agents and representatives of the concerned organisations, all such instructions as may be necessary or appropriate for prompt and effective implementation of the Services;

- provide to the Consultant, Subconsultant, and Personnel any such other assistance and exemptions as may be specified in the SC;

## Access to Land

The Client warrants that the Consultant shall have, free of charge, unimpeded access to all land of which access is required for the performance of the Services.

## Change in the Applicable Law

If, after the date of this Agreement, there is any change in the Applicable Law which increases or decreases the cost of the Services rendered by the Consultant, then the remuneration and direct costs otherwise payable to the Consultant under this Agreement shall be increased or decreased accordingly by agreement between the Parties hereto, and corresponding adjustment shall be made to the amounts referred to in Clause .

## Payments

In consideration of the Services performed by the Consultant under this Agreement, the Client shall make to the Consultant such payments and in such manner as is provided by Clause  of this Agreement.

# PAYMENTS TO THE CONSULTANT

## Lump Sum Remuneration

The Consultant's total remuneration shall not exceed the Agreement Price and shall be a fixed lump sum including all staff costs, incurred by the Consultant in carrying out the Services described in Appendix A. Other reimbursable direct costs expenditure, if any, are specified in the SC.

## Agreement Price

All payments shall be made in local currency as specified in the SC.

## Terms and Conditions of Payment

Payments will be made to the account of the Consultant and according to the payment schedule stated in the SC. Unless otherwise stated in the SC, the first payment shall be made against the provision by the Consultant of an advance payment guarantee for the same amount, and shall be valid for the period stated in the SC. Such guarantee shall be in the form set forth in Appendix F hereto, or in such other form, as the Client shall have approved in writing. Any other payment shall be made after the conditions listed in the SC for such payment have been met, and the Consultant has submitted an invoice to the Client specifying the amount due.

## Period of Payment

- Advance payment to the Consultant shall be affected within the period specified in the SC, after signing of the Agreement between the Parties.

- Any other amount due to the Consultant shall be paid by the Client to the Consultant within twenty-eight (28) days after the Consultant's invoice has been delivered to the Client.

## Delayed Payments

If the Client has delayed payments beyond the period stated in Clause (b), financing charges shall be paid to the Consultant for each day of delay at the rate specified in the SC.

# FAIRNESS AND GOOD FAITH

## Good Faith

The Parties undertake to act in good faith with respect to each other's rights under this Agreement and to adopt all reasonable measures to ensure the realization to the objectives of this Agreement.

# SETTLEMENT OF DISPUTES

## Amicable Settlement

The Parties shall use their best efforts to settle amicably all disputes arising out of or in connection with this Agreement or its interpretation.

## Dispute Settlement

Any dispute between the Parties as to matters arising pursuant to this Agreement which cannot be settled amicably within thirty (30) days after receipt by one Party of the other Party's request for such amicable settlement may be submitted by either Party for settlement in accordance with the provisions of the Arbitration Act, 1940 (Act No. X of 1940) and Rules made thereunder and any statutory modifications thereto.

Special Conditions of Agreement

All notes should be deleted in final text. All blanks should be filled in.

Definitions

"Assignment" means

Authorised Representatives

The Authorised Representatives are the following:

For the Client:

_______________________________

_______________________________

_______________________________

Telephone: ___________________

Facsimile: ___________________

E.Mail:____________________

For the Consultant:

_______________________________ (Name of Project Manager)

_______________________________ (Project)

_______________________________ (Address)

_______________________________

_______________________________

Telephone	: ___________________

Facsimile	: ___________________

E.Mail		:____________________

Taxes

The Client warrants that the Consultant, the Subconsultant and the Personnel shall be exempt from (or that the Client shall pay on behalf of the Consultant, the Subconsultant and the Personnel, or shall reimburse the Consultant, the Subconsultant and the Personnel for) any indirect taxes, duties, fees, levies and other impositions imposed, under the Applicable Law, on the Consultant, the Subconsultant and the Personnel in respect of:

- any payments whatsoever made to the Consultant, Subconsultant and the Personnel (other than nationals or permanent residents of the Government’s country), in connection with the carrying out of the Services;

- any equipment, materials and supplies brought into the Government’s country by the Consultant or Subconsultant for the purpose of carrying out the Services and which, after having been brought into such territories, will be subsequently withdrawn there from by them;

- any equipment imported for the purpose of carrying out the Services and paid for out of funds provided by the Client and which is treated as property of the Client;

- any property brought into the Government’s country by the Consultant, any Subconsultant or the Personnel (other than nationals or permanent residents of the Government’s country), for their personal use and which will subsequently be withdrawn there from by them upon their respective departure from the Government’s country, provided that:

  - the Consultant, Subconsultant and Personnel, shall follow the usual customs procedures of the Government’s country in importing property into the Government’s country; and

  - if the Consultant, Subconsultant or Personnel, do not withdraw but dispose of any property in the Government’s country upon which customs duties and taxes have been exempted, the Consultant, Subconsultant or Personnel, as the case may be, (i) shall bear such customs duties and taxes in conformity with the regulations of the Government’s country, or (ii) shall reimburse them to the Client if they were paid by the Client at the time the property in question was brought into the Government’s country.

Note: This clause may be amended according to agreement between the Parties.

Authority of Authority of Leader of Joint Venture

The leader of the Joint Venture is 	(name of the Member of the Joint Venture)	.

[Note: If the Consultant do not consist of more than one entity, Clause  should be deleted.]

Effectiveness of Agreement

Note: List here any conditions of effectiveness of the Agreement e.g. approval of Consultant’s proposal for appointment of specified key staff members etc.

The date on which this Agreement shall come into effect is the date when the Agreement is signed by both the Parties and the amount of advance payment due upon signing of the Agreement is received by the Consultant.

Termination of Agreement for Failure to Become Effective

The time period shall be 	 days.

[Note: Fill in the time period e.g. one hundred twenty (120) days]

Commencement of Services

The time period shall be 	 days.

[Note: Fill in the time period e.g. one hundred twenty (120) days]

Expiration of Agreement

The time period shall be 	 days.

[Note: Fill in the time period e.g. one hundred twenty (120) days]

Liability of the Consultant

"3.4. Limitation of the Consultants' Liability towards the Client

(a) 	Except in case of gross negligence or willful misconduct on the part of the Consultants or on the part of any person or firm acting on behalf of the Consultants in carrying out the Services, the Consultants, with respect to damage caused by the Consultants to the Client's property, shall not be liable to the Client:

(i) for any indirect or consequential loss or damage; and

(ii) for any direct loss or damage that exceeds by [insert a multiplier, e.g.: three] times the total value of the Contract.

(b) 	This limitation of liability shall not affect the Consultants' liability, if any, for damage to Third Parties caused by the Consultants or any person or firm acting on behalf of the Consultants in carrying out the Services. "

Other Insurances to be Taken out by the Consultant

The risks and the coverages shall be as follows:

- Third Party motor vehicle liability insurance in respect of motor vehicles operated in Pakistan by the Consultant or its Personnel or any Subconsultant or their Personnel, with a minimum coverage of Rs.

- Insurance against loss of or damage to equipment purchased in whole or in part with funds provided under the Agreement.

- Third Party liability insurance with a minimum coverage of Rs

Consultant’s Actions Requiring Client's Prior Approval

{The other actions are: [insert actions].}

Note: If there are no other actions, delete this Clause SC . If the Services consist of or include the supervision of civil works, the following action should be inserted:

The Consultant shall also clear with the Client, before commitments on any action they propose to take under the following:

- Claim from the Contractor for extra payment with full supporting details and Consultant recommendations, if any, for settlement.

- Details of any nominated sub-agreements.

- Any action under terms of Performance Guarantee or Insurance Policy.

- Any action by the Consultant affecting the costs under the following clauses of Conditions of Agreement of the Construction Agreement.

- Adverse Physical Conditions and Artificial Obstructions

- Suspension of Works

- Bonus and Liquidated Damages

- Certificate of Completion of Works

- Defects Liability Certificate

- Forfeiture

- Special Risks

- Frustration

- Final Measurement Statement

- Release of Retention Money

- Any change in the ratios of various currencies of payment.

Documents Prepared by the Consultant to be the Property of the Client

The Client and the Consultant shall not use these documents for purposes unrelated to this Agreement without the prior written approval of the other Party.

Assistance, Coordination and Approvals

- The Client shall make available within 	 days from the Commencement Date, the documents namely

This list if warranted shall be supplemented subsequently.

Lump Sum Remuneration

[Note: In case there are other expenditures in respect of which reimbursement is allowed in addition to the lump sum remuneration, details of such reimbursable direct costs expenditure which may include Subconsultants' costs, printing, communications, travel, accommodation etc., may be indicated herein. Each item shall be specified whether it is payable on the basis of (a) lump sum monthly rate; or (b) reimbursement of actual expenditures.]

Agreement Price

The amount is of the Agreement is

Terms and Conditions of Payment

[Note: Terms and Conditions of Payment provided below is meant for sample reference. This should be edited on case to case basis as per scope of work of the consultancy services of the specific project.]

Payments shall be made according to the following schedule:

Note: (a) “commencement date” may be replaced with “date of effectiveness;” and (d) if applicable, detail further the nature of the report evidencing performance, as may be required, e.g., submission of study or specific phase of study, survey, drawings, draft bidding documents, etc., as listed in Appendix B, Reporting Requirements. In the example provided, the bank guarantee for the repayment is released when the payments have reached 50 percent of the lump- sum price, because it is assumed that at that point, the advance has been entirely set off against the performance of services.

- Twenty (20) percent of the Agreement Price shall be paid on the commencement date pursuant to Clause .

- Ten (10) percent of the lump-sum amount shall be paid upon submission of the inception report

- Twenty-five (25) percent of the lump-sum amount shall be paid upon submission of the interim report.

- Twenty-five (25) percent of the lump-sum amount shall be paid upon submission of the draft final report.

- Twenty (20) percent of the lump-sum amount shall be paid upon approval of the final report.

- The demand guarantee shall be released when the total payments reach fifty (50) percent of the lump-sum amount.

Note: This sample clause should be specifically drafted for each agreement.

Period of Payment

The time period for advance payment shall be 		(   ) days after signing of Agreement by both the Parties. (Fill in the time period e.g. thirty (30) days).

Delayed Payments

Financing charges are eight percent (8%) per annum.

APPENDICES

Appendix A

Description of the Services

- Note: This Appendix will include the final Terms of Reference worked out by the Client and the Consultant during technical negotiations, dates for completion of various tasks, place of performance for different tasks, specific tasks to be approved by Client, etc.

Appendix B

Reporting Requirements

[List format, frequency, and contents of reports; persons to receive them; dates of submission and the number of copies of each submittal etc. If no reports are to be submitted, state here "Not applicable".]

Appendix C

Key Personnel and Subconsultant

[List under:

C-1	Title [and names, if already available], activities of job descriptions, and minimum qualifications of key Personnel to be assigned to work, and staff-months for each

C-2	List of approved Subconsultant (if already available); same information with respect to their Personnel as in C-1

Appendix D

Breakdown of Agreement Price

List here the elements of cost used to arrive at the breakdown of the Agreement Price:

- Remuneration for various items on the basis of rates as mutually agreed

- Other reimbursable direct costs expenditure related to:

  - Support staff, and work charged staff;

  - Office expenditures related to:

    - rentals;

    - furnishing and equipment;

    - operation and maintenance of office, office equipment and furniture, office supplies.

  - Transport including running and maintenance, and other associated costs;

  - Travelling etc.

  - Other costs

- Total, remuneration and reimbursable direct costs expenditure = (a) + (b)

Note:

- Each item of reimbursable direct costs expenditure shall be specified whether it is payable on the basis of (a) lump sum monthly rate; or (b) reimbursement of actual expenditures.

Appendix E

Services and Facilities to be Provided by the Client and Counterpart Personnel to be Made Available to the Consultant by the Client

The Client shall make available the following Services and Facilities:

- Services and Facilities of the Client

The Client shall make available to the Consultant, Subconsultant and the Personnel, for the purposes of the Services and free of any charge, the services, facilities and property described in this Clause at the times and in the manner specified hereunder:

- Lodge Accommodation

If requested by the Consultant, the Client shall provide lodge accommodation, if available, to all Personnel of the Consultant or the Subconsultant when on visit to various parts of the Project area or any other station where such facilities or the lodge accommodation of the Client exists (and provided that the Personnel of the Consultant or the Subconsultant visit that place in connection with the Project) under the same terms and conditions as the Client's staff is entitled.

APPENDIX F

Form of Advance Payments Guarantee

Note: See Clause (a).

Bank Guarantee for Advance Payment

_____________________________ [Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	_________________ [Name and Address of Client]

Date:	________________

ADVANCE PAYMENT GUARANTEE No.:	_________________

We have been informed that ____________ [name of Consulting Firm] (hereinafter called "the Consultants") has entered into Agreement No. _____________ [reference number of the agreement] dated ____________ with you, for the provision of __________________ [brief description of Services] (hereinafter called "the Agreement").

Furthermore, we understand that, according to the conditions of the Agreement, an advance payment in the sum of ___________ [amount in figures] ( ) [amount in words] is to be made against an advance payment guarantee.

At the request of the Consultants, we _______________ [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of ___________ [amount in figures] ( ) [amount in words]1 upon receipt by us of your first demand in writing accompanied by a written statement stating that the Consultants are in breach of their obligation under the Agreement because the Consultants have used the advance payment for purposes other than toward providing the Services under the Agreement.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Consultants on their account number ___________ at _________________ [name and address of Bank].

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Consultants as indicated in copies of certified monthly statements which shall be presented to us. This guarantee shall expire, at the latest, upon our receipt of the monthly payment certificate indicating that the Consultants have made full repayment of the amount of the advance payment, or on the __ day of ___________, 2___,2 whichever is earlier. Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458.

_____________________

[Signature(s)]

Note:	All italicized text is for indicative purposes only to assist in preparing this form and shall be deleted from the final product.

Telephone line will be provided by the LDA at the allocated office premises, however the cost will be borne by the bidder

It has been the usual practice that consultants prepare plans and documents, carryout analyses and left the client departments at the same level of technical capacity. The purpose of housing the consultants in client’s premises and providing counterpart team is to let them gain technical expertise and master planning techniques for empowering them to carry out master planning of other cities on their own.

Indicate the total costs, net of local taxes, to be paid by the Client in Pak Rupees.  Such total costs must coincide with the sum of the relevant Subtotals indicated in all Forms FIN-3 provided with the Proposal.

The ToRs will be finalized in the pre-proposal conference

The sample size for each survey will be finalized in Pre-Proposal Conference

1	The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency(ies) of the advance payment as specified in the Agreement, or in a freely convertible currency acceptable to the Client.

2	Insert the expected expiration date. In the event of an extension of the time for completion of the Agreement, the Client would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Client might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Client’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”